## Role 9 - SVP Integrated Production
Bug ID | Role | Severity | Category | Component | File:Line | Description | Steps to Reproduce | Expected Behavior | Actual Behavior | Impact | Status
R09-001 | SVP Integrated Production | CRITICAL | Environment Issue | Firebase Configuration | src/lib/firebase.js:6 | Firebase is initialized without any validation of required environment variables. The firebaseConfig object reads seven VITE_FIREBASE_* variables from import.meta.env and passes them directly to initializeApp(). If any required variable (apiKey, authDomain, projectId) is undefined, Firebase will initialize with an invalid configuration, producing cryptic runtime errors instead of a clear startup failure. There is no guard, no early throw, and no .env presence check. | 1. Remove or leave blank the VITE_FIREBASE_API_KEY variable from .env 2. Run 'npm run build && npm run preview' or 'npm run dev' 3. Open the application in a browser 4. Attempt to log in or access any authenticated page | Application should fail fast with a clear, descriptive error message indicating which Firebase environment variables are missing, and prevent rendering of components that depend on Firebase. | Firebase initializes with undefined values, leading to obscure 'auth/invalid-api-key' or 'FirebaseError' messages at runtime that are difficult to diagnose. The app may partially render before crashing. | Deployment to any new environment (staging, production, CI) without all Firebase env vars will produce a broken application with no actionable error message, causing extended downtime and debugging time. | OPEN
R09-002 | SVP Integrated Production | CRITICAL | Deploy Risk | AI Services - API Key Exposure | src/lib/schema-generator/schemaGeneratorService.js:38 | Three of the five AI service modules (schemaGeneratorService.js, imageAltService.js, metaGeneratorService.js) allow direct API key usage in production without blocking it. Unlike suggestionService.js which throws an error when import.meta.env.PROD is true and only an apiKey is configured, these three services silently fall through to direct browser API calls. The VITE_CLAUDE_API_KEY would be embedded in the production JavaScript bundle, visible in browser DevTools Network tab. | 1. Set VITE_CLAUDE_API_KEY in .env and leave VITE_AI_PROXY_URL unset 2. Run 'npm run build' 3. Open the production build in a browser 4. Navigate to Schema Generator, Image Alt Generator, or Meta Generator 5. Open DevTools > Network and trigger an AI feature 6. Inspect the outgoing request headers | All AI services should block direct API key usage in production builds, consistent with the behavior of suggestionService.js which throws an explicit error in production mode. | schemaGeneratorService.js (line 38), imageAltService.js (line 38), and metaGeneratorService.js (line 38) allow direct API key usage regardless of build mode, exposing the API key in the client-side JavaScript bundle. | If VITE_CLAUDE_API_KEY is set in a production deployment, the Anthropic API key is exposed to all users, enabling unauthorized API usage, potential billing abuse, and a security breach requiring key rotation. | OPEN
R09-003 | SVP Integrated Production | HIGH | Monitoring Gap | ErrorBoundary | src/components/shared/ErrorBoundary.jsx:21 | The ErrorBoundary component only logs errors in development mode (import.meta.env.DEV) and has no integration with any external error monitoring service (Sentry, LogRocket, Datadog, etc.). In production builds, componentDidCatch silently swallows the error and errorInfo. There is also no global window error or unhandledrejection handler anywhere in the application (confirmed via codebase search). Production errors are completely invisible to the engineering team. | 1. Deploy the application to production (npm run build && serve) 2. Trigger a rendering error in any component (e.g., pass invalid props to a chart component) 3. Check if any error telemetry is sent to an external service 4. Check server logs for any error reports | Production errors should be reported to an error monitoring service (e.g., Sentry) with full context including error message, component stack, user info, and URL. Global unhandled errors and promise rejections should also be captured. | Errors are only console.error'd in development. In production, errors are caught by ErrorBoundary but not reported anywhere. No global error handlers exist. Production errors are completely invisible. | The team has zero visibility into production errors. Users may encounter broken pages repeatedly without anyone knowing, leading to user churn, data loss, and inability to prioritize fixes. Critical issues like chunk loading failures or Firebase outages would go undetected. | OPEN
R09-004 | SVP Integrated Production | HIGH | Bundle Size | Component-Level jsPDF Imports | src/components/meta-generator/CompetitorAnalysisPanel.jsx:20 | Multiple UI components directly import jsPDF and jspdf-autotable at the top level instead of using dynamic imports. These are large libraries (~300KB combined) that get statically bundled into each component's chunk. Affected files: CompetitorAnalysisPanel.jsx (line 20), VPATReportGenerator.jsx (line 18), BatchAuditPanel.jsx (line 21). While the vite.config.js has manualChunks for 'vendor-jspdf', these static imports force the chunk to load whenever any of these components mount, even if the user never triggers a PDF export. | 1. Run 'npm run build' and inspect the output chunk sizes 2. Navigate to the Meta Generator page and open Competitor Analysis 3. Observe network requests in DevTools 4. Note that the jsPDF vendor chunk loads immediately on component mount, not when 'Export PDF' is clicked | jsPDF and jspdf-autotable should be dynamically imported (e.g., const jsPDF = (await import('jspdf')).default) only when the user actually clicks an export button, reducing initial component load by ~300KB. | jsPDF is statically imported at the module top level in at least 4 component files, causing the ~300KB vendor-jspdf chunk to be downloaded eagerly whenever those components mount. | Users on slow connections experience unnecessary delays loading components that include PDF export functionality. The jsPDF chunk downloads even when users never intend to export, wasting bandwidth and increasing Time to Interactive. | OPEN
R09-005 | SVP Integrated Production | HIGH | Code Splitting | ReadabilityDashboard Lazy Imports | src/components/readability/ReadabilityDashboard.jsx:10 | ReadabilityDashboard uses React.lazy() directly for ReadabilityCategoryChart and ReadabilityLLMPreview (lines 10 and 12), bypassing the application's lazyWithRetry utility. The lazyWithRetry wrapper (src/utils/lazyWithRetry.js) provides retry logic with 3 attempts and 1-second delays for chunk loading failures. By using raw lazy(), these sub-components lack retry resilience and will crash into the ErrorBoundary on the first transient network failure instead of retrying. | 1. Open the Readability tool and run an analysis to reach the dashboard 2. Simulate a slow/unreliable network (DevTools > Network > Offline for 2 seconds, then back) 3. Switch to the 'Score Details' tab which loads ReadabilityCategoryChart 4. Observe the chunk load failure | ReadabilityCategoryChart and ReadabilityLLMPreview should use lazyWithRetry() consistent with all other lazy-loaded components in App.jsx, providing automatic retry on transient network failures. | These components use bare React.lazy() and will fail immediately on any chunk loading error, showing the error boundary fallback UI with no automatic retry. | Users on unreliable networks (mobile, public WiFi) will see error screens when viewing readability analysis results, despite the rest of the application being resilient to transient chunk load failures. | OPEN
R09-006 | SVP Integrated Production | HIGH | Error Logging | lazyWithRetry Production Logging | src/utils/lazyWithRetry.js:37 | The lazyWithRetry utility only logs chunk loading failures in development (import.meta.env.DEV check on line 37). In production, when a module fails to load after 3 retries, the error is silently re-thrown with a generic message. The original error details (network status, URL, error type) are lost. Combined with the lack of production error monitoring (R09-A-003), failed lazy loads in production are completely invisible to the team. | 1. Deploy to production 2. Deploy a new version that changes chunk hashes 3. A user with cached HTML but stale chunk references visits the site 4. lazyWithRetry fails 3 times on the old chunk URL 5. Check if any error details are available anywhere | Chunk loading failures in production should be logged to an error reporting service with the original error, module name, retry count, and the failed chunk URL, allowing the team to monitor deployment-related issues. | In production, the original error is discarded and replaced with a generic 'Failed to load [module]. Please check your connection and try again.' message. No telemetry is sent. | After deployments, users with stale caches may encounter persistent chunk loading failures. Without production logging, the team cannot measure the frequency of these failures or determine if a deployment caused widespread issues. | OPEN
R09-007 | SVP Integrated Production | HIGH | Deploy Risk | Accessibility AI Suggestion Service | src/lib/accessibility/aiSuggestionService.js:26 | The accessibility AI suggestion service has inconsistent production behavior compared to the main suggestionService.js. When VITE_CLAUDE_API_KEY is set and VITE_AI_PROXY_URL is not set, the accessibility service only emits a console.warn (line 27) in production but still proceeds with direct API access, while the main suggestionService.js throws a hard error to block production API key exposure. This creates an inconsistency where one service blocks and another merely warns. | 1. Set VITE_CLAUDE_API_KEY and leave VITE_AI_PROXY_URL unset 2. Build for production: npm run build 3. Open the app and navigate to Accessibility Analyzer 4. Run an audit and click 'Get AI Fix Suggestions' 5. Check DevTools Console and Network tab | All AI services should have consistent behavior in production: either block direct API key usage (throw error) or use a proxy. The accessibility service should throw an error in production like suggestionService.js does. | aiSuggestionService.js logs a console.warn but proceeds with direct API calls in production, exposing the API key in the browser. This is inconsistent with suggestionService.js which throws a blocking error. | Security inconsistency across AI services means that even if the team believes they have blocked direct API access in production, the accessibility module still exposes it, creating a false sense of security. | OPEN
R09-008 | SVP Integrated Production | MEDIUM | Build Issue | Vite Build Configuration | vite.config.js:25 | The Vite build configuration raises the chunkSizeWarningLimit to 600KB (line 25), which is 3x the default 200KB limit. The comment says 'Increase warning limit since we have lazy loading,' but this effectively suppresses warnings about oversized chunks. While manualChunks are configured for vendor libraries, application code chunks that grow beyond 200KB will not trigger any warning during builds, hiding bundle size regressions. | 1. Add a large new dependency to a lazy-loaded component 2. Run 'npm run build' 3. Observe that no chunk size warnings appear even if a chunk exceeds 400KB 4. Compare with default Vite behavior (200KB warning) | The chunkSizeWarningLimit should remain at or near the default 200KB, or a build analysis step (e.g., rollup-plugin-visualizer) should be configured to detect bundle size regressions. Vendor chunks that are intentionally large should be handled differently. | The 600KB limit silently allows application chunks to grow to 3x the recommended size without any CI/build warning, making it easy to introduce bundle size regressions undetected. | Bundle size regressions can accumulate silently over time, degrading page load performance and Core Web Vitals scores, particularly for users on mobile or slow connections. | OPEN
R09-009 | SVP Integrated Production | MEDIUM | Caching Gap | Analysis Cache - localStorage | src/lib/readability/utils/analysisCache.js:44 | The readability analysis caching system stores large analysis results in localStorage (line 107), which has a typical 5-10MB limit shared across the entire domain. Each cached analysis includes full check results, recommendations, LLM extractions, and AI assessments. With a MAX_CACHE_ENTRIES of 20 and no per-entry size limit, the cache can quickly exhaust localStorage quota, which is also used by storageHelpers.js for checklist data, time entries, filter presets, and project metadata. The pruneCache function only limits count, not total byte size. | 1. Run readability analyses on 10-15 different content-heavy URLs 2. Each analysis caches category scores, check results, recommendations, LLM extractions, and AI assessments 3. Open DevTools > Application > Local Storage and observe total usage 4. Try to use other localStorage-dependent features (filter presets, time tracking) | The caching layer should enforce a total byte budget (e.g., 2MB) rather than just an entry count. It should also gracefully handle quota exceeded errors without corrupting other localStorage data. | The cache enforces only a count limit of 20 entries with no size constraints. Large analyses can push total localStorage usage near the 5MB limit, causing QuotaExceededError for other features. The catch block on line 109 silently ignores quota errors. | Users who analyze many pages will lose checklist data, filter presets, and time tracking entries when localStorage fills up. The silent error handling means users won't know their data was not saved. | OPEN
R09-010 | SVP Integrated Production | MEDIUM | Error Logging | Console.log in Production Code | src/components/readability/ReadabilityDashboard.jsx:448 | A console.log statement exists in production component code at ReadabilityDashboard.jsx line 448: 'console.log('Custom weights applied:', weights)'. This is a debugging artifact that was not cleaned up. More broadly, the codebase has over 100 console.error/console.warn calls across hooks and services that output to the browser console in production. While console.error calls serve some purpose during development, they provide no value in production and can leak internal implementation details to users who open DevTools. | 1. Open the Readability tool in a production build 2. Run an analysis and view the dashboard 3. Click 'Adjust Weights' and change any weight slider 4. Open DevTools > Console 5. Observe the 'Custom weights applied:' log with full weight data | No console.log statements should exist in production component code. console.error calls should be replaced with or supplemented by a structured logging service that can be disabled in production or routed to a monitoring service. | A console.log debugging artifact exists in ReadabilityDashboard.jsx. Additionally, 100+ console.error calls across the codebase produce noisy, unstructured output in production browsers with no centralized collection. | Console.log leaks internal state data to any user viewing DevTools. The volume of console.error output in production makes it difficult for developers to distinguish real issues from expected error handling. No production visibility is gained from these logs. | OPEN
R09-011 | SVP Integrated Production | MEDIUM | Bundle Size | Eagerly Loaded Public Pages | src/App.jsx:25 | Seven public marketing pages (LandingPage, AboutPage, FeaturesPage, FeatureDetailPage, HelpCenterPage, GettingStartedPage, NotFoundPage) are eagerly imported in App.jsx (lines 25-31). These are loaded in the initial bundle for all users, including authenticated users who are redirected to /app and never see these pages. The comment says 'eager load for fast marketing site,' but authenticated users pay the cost of downloading this code without ever using it. Additionally, components like KeyboardShortcuts, OnboardingWalkthrough, FeedbackWidget, CookieConsent, and CommandPalette are also eagerly loaded (lines 48-52). | 1. Log into the application 2. Open DevTools > Network and observe initial JavaScript bundle sizes 3. Note that public page code (LandingPage, AboutPage, FeaturesPage, etc.) is included in the main chunk 4. Navigate only within /app routes and never visit any public page | Public marketing pages should be lazy loaded since authenticated users never visit them. The initial bundle for authenticated users should only include auth components, navigation, and the HomePage. At minimum, non-critical components like KeyboardShortcuts, OnboardingWalkthrough, and CookieConsent should be lazy loaded. | Public pages and several utility components are statically imported, increasing the initial bundle size for all users regardless of their route. Authenticated users download marketing page code they will never use. | Increased initial bundle size leads to slower Time to Interactive, especially on mobile devices. Authenticated users (the primary audience) download unnecessary code for marketing pages, adding potentially 50-100KB+ of unused JavaScript to their initial load. | OPEN
R09-012 | SVP Integrated Production | MEDIUM | Dependency Risk | Package Dependencies | package.json:19 | The package.json uses caret (^) version ranges for all 18 production dependencies. While this is common, several dependencies are pinned to major versions that may have breaking changes in minor releases. Notable concerns: firebase ^12.7.0 (Firebase SDK is large and frequently updated with potential breaking changes), pdfjs-dist ^5.4.530 (uncommon version pattern suggesting a newer release train), and jspdf ^4.0.0 (major version 4 may have API changes from v3). There is no package-lock.json audit step in the build scripts, and no 'npm audit' or security scanning in the CI pipeline (no CI configuration files found). | 1. Delete node_modules and package-lock.json 2. Run 'npm install' 3. Verify that the installed versions may differ from the original lockfile 4. Run 'npm audit' to check for known vulnerabilities 5. Look for CI/CD configuration (none found in repository root) | The project should have a lockfile integrity check in CI, an 'npm audit' step in the build/test pipeline, and ideally Dependabot or Renovate configured for automated dependency updates with security alerts. | No CI/CD configuration was found. There is no automated dependency security scanning. Caret ranges mean different installations may resolve to different minor versions. No 'npm audit' step exists in package.json scripts. | Without automated dependency auditing, known vulnerabilities in transitive dependencies may go undetected. Different team members or deployment environments may install different dependency versions, leading to 'works on my machine' issues. | OPEN
R09-013 | SVP Integrated Production | MEDIUM | Deploy Risk | Build Scripts - No CI/CD Configuration | package.json:7 | The package.json contains only basic scripts (dev, build, preview, lint, test). There are no CI/CD configuration files in the repository (no .github/workflows, no .gitlab-ci.yml, no Dockerfile, no vercel.json, no firebase.json for hosting). The build process has no automated quality gates: no lint step in build, no test step before deploy, no bundle size budget enforcement, no lighthouse CI, and no environment variable validation. | 1. Search for CI/CD configuration files in the repository root 2. Review package.json scripts for pre-build or post-build hooks 3. Check for deployment configuration files 4. Verify that 'npm run build' does not run lint or tests | A production application should have CI/CD configuration that: runs lint, runs tests, builds the application, validates environment variables, checks bundle sizes against budgets, and deploys to the appropriate environment. A pre-build script should verify required env vars. | No CI/CD pipeline configuration exists. The 'build' script is just 'vite build' with no pre-build validation. There is no automated deployment process, no environment variable validation at build time, and no quality gates. | Without CI/CD, deployments are manual and error-prone. Broken code can be deployed without running tests. Missing environment variables will not be caught until runtime. There is no automated rollback capability. | OPEN
R09-014 | SVP Integrated Production | MEDIUM | Caching Gap | Vite Build - No Content Hash in Config | vite.config.js:11 | The Vite build configuration does not explicitly configure output file naming with content hashes for assets beyond the default. While Vite does add hashes to JS chunks by default, there is no explicit configuration for CSS, font, or image asset naming patterns. More critically, there is no configuration for service worker, cache headers, or asset manifest generation. The application has no service worker for offline caching or cache-first strategies, meaning repeat visits always require full network requests for HTML and uncached assets. | 1. Run 'npm run build' and inspect dist/assets directory 2. Check for a service worker or workbox configuration 3. Deploy and check HTTP cache headers for static assets 4. Revisit the site on a slow connection and note no offline support | Production builds should include: explicit asset naming with content hashes, a service worker for cache-first strategies on static assets, proper cache-control header configuration guidance, and an asset manifest for cache invalidation. | No service worker exists. No PWA configuration. No explicit cache-control header guidance. Static assets rely solely on whatever headers the hosting provider sets by default. | Without a service worker, repeat visits are slower than necessary. Users on unreliable connections have no offline fallback. The absence of explicit caching strategy means the application's performance depends entirely on hosting provider defaults. | OPEN
R09-015 | SVP Integrated Production | LOW | Build Issue | Vite Config - Source Maps | vite.config.js:5 | The Vite configuration does not explicitly set the build.sourcemap option. By default, Vite does not generate source maps for production builds. While this is often desired for security (not exposing source code), it makes debugging production issues nearly impossible since stack traces from the ErrorBoundary or any reported errors will reference minified/mangled variable names and line numbers that don't correspond to the source code. | 1. Run 'npm run build' 2. Check dist/assets for .map files (none present by default) 3. Trigger a production error 4. Observe that the error stack trace references minified code with unhelpful variable names | Source maps should be generated during production builds and either uploaded to an error monitoring service (Sentry source map upload) or served with restricted access. The build.sourcemap option should be explicitly set to 'hidden' to generate maps without referencing them in the output files. | No source maps are generated for production. Combined with the lack of error monitoring (R09-A-003), production error debugging requires reproducing issues locally. | Production error investigation is significantly slower. Engineers must manually try to reproduce issues locally since production stack traces are unreadable. This increases mean time to resolution for production incidents. | OPEN
R09-016 | SVP Integrated Production | LOW | Code Splitting | Vendor Chunk Configuration | vite.config.js:20 | The manualChunks configuration in vite.config.js groups 'htmlparser2', 'franc', and 'jszip' together as 'vendor-readability' (line 20). However, jszip is also used by the audit module (src/lib/audit/zipProcessor.js) for processing ZIP uploads, not just readability. Grouping jszip with readability-specific libraries means the audit tool unnecessarily downloads htmlparser2 and franc when it only needs jszip. Additionally, libraries like 'date-fns', 'chart.js', 'react-chartjs-2', 'mammoth', and 'pdfjs-dist' are not included in manualChunks, which may lead to suboptimal chunk distribution. | 1. Run 'npm run build' and examine chunk composition 2. Navigate to the Audit tool and upload a ZIP file 3. Observe that the vendor-readability chunk (containing htmlparser2 + franc + jszip) is loaded 4. Note that htmlparser2 and franc are not needed for audit ZIP processing | jszip should be in its own vendor chunk since it's shared across multiple tools. Other large libraries (date-fns, mammoth, pdfjs-dist) should also be in manualChunks to prevent duplication across lazy-loaded routes. | jszip is bundled with readability-only libraries. Other large dependencies like chart.js, mammoth, and pdfjs-dist have no explicit chunk configuration and may be duplicated across multiple route chunks. | Suboptimal chunk splitting causes users to download unnecessary code. The audit tool downloads ~200KB of unused readability libraries (htmlparser2, franc) when it only needs jszip (~90KB). Users of multiple tools may also download duplicate copies of un-chunked shared libraries. | OPEN
R09-017 | SVP Integrated Production | HIGH | Deploy Risk | Meta Generator - PDF Worker CDN | src/lib/meta-generator/metaGeneratorService.js:123 | The PDF extraction function loads the pdf.js web worker from an external CDN (cdnjs.cloudflare.com) at runtime using a protocol-relative URL. This creates multiple deployment risks: (1) the CDN could be unavailable or blocked by corporate firewalls, (2) strict Content Security Policy headers will block external script loading, (3) the protocol-relative URL '//' can cause issues in certain contexts, and (4) the version is dynamically interpolated from the installed package version which may not match available CDN builds. | 1. Upload a PDF file to the Meta Data Generator tool. 2. Block access to cdnjs.cloudflare.com via browser DevTools network blocking or configure a strict CSP. 3. Attempt to process the PDF. 4. Observe the failure with no user-facing error message explaining the cause. | The pdf.js worker should be bundled locally or loaded from a self-hosted path via Vite's asset handling (e.g., new URL('pdfjs-dist/build/pdf.worker.min.js', import.meta.url)), with a fallback mechanism if the worker fails to load. | The worker is loaded from `//cdnjs.cloudflare.com/ajax/libs/pdf.js/${pdfjsLib.version}/pdf.worker.min.js` which fails if the CDN is unreachable, CSP blocks external scripts, or the dynamically interpolated version does not match an available CDN asset path. | PDF processing is completely broken for users behind corporate firewalls, in environments with strict CSP, or during CDN outages. No error message explains why PDF upload fails, leading to user confusion and support tickets. | OPEN
R09-018 | SVP Integrated Production | MEDIUM | Error Logging | AuthContext - Silent Error Swallowing | src/contexts/AuthContext.jsx:187-189 | The deleteAccount function silently catches and ignores Firebase Storage file deletion errors (line 187-189: empty catch block with comment 'Silently fail if no files exist or storage error'). Similarly, fetchUserProfile at line 217 silently swallows Firestore read errors. If storage deletion fails due to permission issues or partial failures, the user receives a success toast ('Your account has been permanently deleted') even though their files remain in Firebase Storage, creating orphaned data and potential GDPR/privacy compliance issues. | 1. Create a user account and upload file attachments to projects. 2. Modify Firebase Storage rules to temporarily deny delete access. 3. Delete the account via the settings page. 4. Observe the success toast message. 5. Check Firebase Storage console - orphaned user files remain. | Storage deletion failures should be logged to a monitoring service and the user should be informed if some data could not be fully removed. A retry mechanism or background cleanup job should handle failed deletions. | Storage deletion errors are silently caught with an empty catch block (line 187). The function proceeds to delete the auth user and shows a success toast. Orphaned storage files remain with no record of the failure. | Potential GDPR/CCPA compliance violation where user data persists after an account deletion request. No monitoring trail of cleanup failures. Orphaned files accumulate in Firebase Storage, increasing storage costs over time. | OPEN
R09-019 | SVP Integrated Production | MEDIUM | Deploy Risk | Hosting Configuration - SPA Routing | index.html:1-14 | The application is a single-page application using BrowserRouter (client-side routing with history API), but there is no hosting/server configuration file defining SPA fallback routing. Without a hosting config (firebase.json, netlify.toml, vercel.json, _redirects, etc.), direct navigation to any route other than '/' (e.g., /app/audit, /login, /features/planner) will return a 404 from the hosting server because those paths do not correspond to physical files. | 1. Run 'npm run build'. 2. Deploy the dist/ folder to a static hosting provider without SPA configuration. 3. Navigate to the app and click through to /app/audit. 4. Refresh the browser page. 5. Observe a 404 error because the server has no /app/audit/index.html file. | A hosting configuration file should define that all routes (except for actual static asset paths) should serve index.html, enabling client-side routing to work correctly on page refreshes and direct URL navigation. | No hosting configuration file exists. Client-side routes like /app/audit, /app/readability, /login, /about, etc. will 404 on page refresh or direct navigation unless the hosting provider is manually configured outside the project. | Users who bookmark deep links, share URLs, or simply refresh the page will encounter 404 errors. Search engine crawlers will also fail to index any route other than the root, negating SEO efforts for the marketing pages. | OPEN
R09-020 | SVP Integrated Production | CRITICAL | Error Logging | ErrorBoundary | src/components/shared/ErrorBoundary.jsx:21 | ErrorBoundary only logs errors to console.error in development mode (import.meta.env.DEV). In production, componentDidCatch is effectively a no-op -- errors that crash component trees are silently swallowed with no telemetry, no external error reporting service integration (e.g., Sentry, DataDog, LogRocket), and no server-side logging. This means production runtime errors will be invisible to the engineering and operations teams. | 1. Deploy application to production environment. 2. Trigger a rendering error in any lazy-loaded component (e.g., corrupt API response in ReadabilityDashboard). 3. Observe that the ErrorBoundary catches the error and shows the fallback UI. 4. Check server logs, monitoring dashboards, or any external logging service. | Production errors caught by ErrorBoundary should be reported to an external error monitoring service (Sentry, Bugsnag, etc.) with stack trace, component stack, user context, and page route. | In production, componentDidCatch sets state but performs no logging or external reporting. Errors are completely invisible to the operations team. | Production crashes go undetected. Teams cannot triage, prioritize, or fix production errors. Users experience broken pages with no visibility into frequency or root cause, degrading platform reliability and trust. | OPEN
R09-021 | SVP Integrated Production | HIGH | Bundle Size | ReportBuilderPage | src/components/reports/ReportBuilderPage.jsx:33 | ReportBuilderPage statically imports both jsPDF and html2canvas at the top level. These are heavyweight libraries (jsPDF ~300KB, html2canvas ~200KB minified) that are only needed when the user clicks 'Export'. They are not listed in vite.config.js manualChunks and not dynamically imported, meaning they are bundled into the main ReportBuilderPage chunk and loaded eagerly when the page mounts, even if the user never exports. | 1. Navigate to the Report Builder page. 2. Open browser DevTools Network tab. 3. Observe the chunk loaded for ReportBuilderPage. 4. Note that jsPDF and html2canvas are included in the chunk even though no export has been triggered. | jsPDF and html2canvas should be dynamically imported (import()) inside the exportReport function, only loaded when the user actually triggers an export operation. | Both libraries are statically imported at the top of the file (lines 33-34), increasing the initial chunk size by approximately 500KB for all users who visit the Report Builder, regardless of whether they export. | Unnecessarily inflated bundle size for the Report Builder page. Slower initial page load, especially on mobile or slow connections. This directly impacts Core Web Vitals (LCP, TTI) for a page that may be frequently visited by project managers. | OPEN
R09-022 | SVP Integrated Production | HIGH | Deploy Risk | SEO Configuration | src/config/seo.js:9 | The site URL is hardcoded as 'https://contentstrategyportal.com' with a TODO comment 'Update with actual domain'. This value is used for all canonical URLs, Open Graph meta tags, Twitter Card URLs, schema.org JSON-LD, breadcrumb schemas, and HowTo schema throughout the application. If the actual production domain differs (e.g., staging, preview deployments, or a different production domain), all SEO metadata will point to an incorrect or non-existent domain. | 1. Open src/config/seo.js. 2. Observe SITE_URL is hardcoded to 'https://contentstrategyportal.com'. 3. Deploy to staging or a preview environment. 4. Inspect <head> meta tags -- all canonical URLs, og:url, and schema.org markup reference the hardcoded domain. | SITE_URL should be sourced from an environment variable (e.g., import.meta.env.VITE_SITE_URL) with the hardcoded value as a fallback. This enables correct canonical URLs and schema markup across all deployment environments. | SITE_URL is a hardcoded constant string. There is no environment variable override. All environments (dev, staging, production) generate SEO metadata pointing to 'https://contentstrategyportal.com'. | Staging and preview deployments generate incorrect canonical URLs, potentially causing search engine indexing issues. If the production domain is different from the hardcoded value, all SEO meta tags, Open Graph tags, and structured data will reference a non-existent URL, harming search visibility and social sharing. | OPEN
R09-023 | SVP Integrated Production | HIGH | Monitoring Gap | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:448 | The ReadabilityWeightConfig onChange handler contains a console.log statement: console.log('Custom weights applied:', weights). This is debug logging left in production code. More critically, there is no actual weight application logic -- the onChange callback only logs and does nothing else. When users adjust weights via the UI, the changes are silently discarded. | 1. Navigate to a completed readability analysis. 2. Open the 'Score Details' tab. 3. Click 'Adjust Weights'. 4. Modify any weight slider. 5. Observe that scores do not recalculate and the console shows the log message. | Weight changes should trigger a score recalculation. The console.log should be removed from production code and replaced with actual weight application logic or at minimum a monitoring event. | The onChange handler only calls console.log. Weights are never applied. The debug statement ships to production. | Users who attempt to customize scoring weights see no effect, leading to confusion and perceived broken functionality. The console.log pollutes production logs and leaks implementation details. The feature appears broken from a user perspective. | OPEN
R09-024 | SVP Integrated Production | HIGH | Code Splitting | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:11 | ReadabilityDashboard uses React.lazy for ReadabilityCategoryChart and ReadabilityLLMPreview, but eagerly imports seven other large components (ReadabilityRecommendations, ReadabilityIssuesTable, ReadabilityCrossToolLinks, ReadabilityPDFPreview, ReadabilityQuotableHighlighter, ReadabilityWeightConfig, ReadabilityScoreCard) that are displayed conditionally based on tab selection. Only one tab panel is visible at a time, yet all tab components are loaded upfront. Additionally, ReadabilityPDFPreview (which internally imports heavy PDF generation libraries) is eagerly imported even though it only renders when the user clicks 'Export as PDF'. | 1. Open the ReadabilityDashboard component. 2. Observe that only ReadabilityCategoryChart and ReadabilityLLMPreview use lazy(). 3. Components for inactive tabs (recommendations, issues) and modals (PDF preview, weight config) are statically imported. 4. Check bundle analyzer output for the ReadabilityDashboard chunk. | Tab content components should be lazily loaded. At minimum, ReadabilityPDFPreview (which gates PDF export libraries), ReadabilityWeightConfig, and the per-tab components should use React.lazy or dynamic import to avoid loading unused code. | Only 2 of 9 imported child components use lazy loading. The remaining 7 are statically imported and bundled into the ReadabilityDashboard chunk, including modal components that may never render. | Inflated chunk size for the readability results page, which is the most frequently visited page in the readability workflow. Slower time-to-interactive on the results page, degrading user experience especially on repeat analyses. | OPEN
R09-025 | SVP Integrated Production | MEDIUM | Code Splitting | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:10 | ReadabilityDashboard uses bare React.lazy() for sub-component lazy loads (ReadabilityCategoryChart on line 10, ReadabilityLLMPreview on line 12) instead of the application's lazyWithRetry utility. The App.jsx file consistently uses lazyWithRetry for all route-level lazy loads to provide automatic retry logic for chunk loading failures. These sub-component lazy imports bypass that pattern, making them vulnerable to transient network failures without retry. | 1. Load the ReadabilityDashboard results page. 2. Throttle the network to simulate an unreliable connection. 3. Observe that ReadabilityCategoryChart or ReadabilityLLMPreview fails to load on the first attempt. 4. Compare with route-level components that use lazyWithRetry and successfully retry. | Sub-component lazy imports should use lazyWithRetry(() => import('./ReadabilityCategoryChart'), 'ReadabilityCategoryChart') to get automatic retry on chunk load failures, consistent with the app-wide pattern. | Lines 10 and 12 use bare lazy(() => import(...)) instead of lazyWithRetry(() => import(...)). If the chunk fails to load, there is no retry and the user immediately sees an error boundary fallback. | Users on unreliable networks may see broken dashboard sections (blank chart area, broken LLM preview) that could have been recovered with automatic retries, reducing perceived reliability of the readability tool. | OPEN
R09-026 | SVP Integrated Production | MEDIUM | Build Issue | Vite Configuration | vite.config.js:25 | The chunkSizeWarningLimit is set to 600KB, which is 20% above Vite's default of 500KB. The comment states 'Increase warning limit since we have lazy loading', but this masks genuine bundle size problems. Several dependencies are missing from manualChunks configuration: html2canvas (used in ReportBuilderPage), chart.js and react-chartjs-2 (used across multiple dashboard components), mammoth (used for document parsing), pdfjs-dist (used for PDF preview), and react-markdown. These libraries will be bundled into their respective component chunks without dedicated vendor splitting. | 1. Run 'vite build'. 2. Observe the build output for chunk sizes. 3. Note that html2canvas, chart.js, react-chartjs-2, mammoth, pdfjs-dist are not listed in manualChunks. 4. Verify that the 600KB warning limit suppresses warnings for oversized chunks. | manualChunks should include all heavy vendor libraries (html2canvas, chart.js, react-chartjs-2, pdfjs-dist, mammoth, react-markdown). The chunkSizeWarningLimit should remain at the default 500KB to surface genuine problems. Each heavy vendor should be in its own chunk for optimal caching. | Only 5 vendor groups are defined in manualChunks. At least 6 heavy dependencies are missing. The elevated warning limit hides chunk size violations. | Suboptimal bundle splitting leads to larger-than-necessary downloads when users navigate to pages using these unlisted dependencies. Browser cache invalidation is also suboptimal -- updating any component that shares a chunk with chart.js forces re-download of chart.js even if it has not changed. | OPEN
R09-027 | SVP Integrated Production | MEDIUM | Error Logging | AuthContext | src/contexts/AuthContext.jsx:217 | The fetchUserProfile function silently catches and ignores all errors with an empty catch block: 'catch { // Silently fail - profile will be null }'. Similarly, the deleteAccount storage cleanup at line 187 uses an empty catch block. When Firestore is unavailable, has permission errors, or has network issues, the user profile fetch failure is completely invisible. The user will see the app in a degraded state (no profile data, no role information) with no error indication, no logging, and no monitoring alert. | 1. Simulate a Firestore outage or permission error (e.g., modify security rules). 2. Log in to the application. 3. Observe that user profile is null (no role, no name, no avatar). 4. Check any logging or monitoring -- no error is recorded. | Profile fetch failures should be logged (at minimum console.error, ideally to an external monitoring service). The user should see a graceful degradation message or retry mechanism. The catch block should differentiate between 'no profile exists' vs 'Firestore error'. | All errors are silently swallowed. The user sees a degraded experience (null profile, default role) with no explanation and no way for the team to diagnose the issue. | Users may lose access to role-gated features (like the readability checker, which checks canRunReadabilityCheck permission) because their role defaults to 'content_writer' when the profile fails to load. Operations team has no visibility into profile loading failures. | OPEN
R09-028 | SVP Integrated Production | MEDIUM | Dependency Risk | Package Configuration | package.json:23 | The lucide-react dependency is pinned to version '^0.294.0', which is a pre-1.0 release. Pre-1.0 semver ranges with caret (^) allow minor version upgrades that may include breaking changes per semver conventions for pre-1.0 packages. lucide-react is used extensively throughout the entire application (every component imports icons from it). A breaking change in icon names, props, or tree-shaking behavior could break the entire UI across all components simultaneously during npm install or CI builds. | 1. Open package.json. 2. Observe lucide-react version is '^0.294.0'. 3. Run 'npm install' in a fresh environment. 4. If a newer 0.x version has been published with breaking changes (icon renames, removed icons, changed exports), the install will pull it in. | lucide-react should be pinned to an exact version (e.g., '0.294.0') or the caret range should be replaced with a tilde ('~0.294.0') to prevent unexpected breaking changes. Alternatively, upgrade to a stable 1.x release if available. | The caret range allows any 0.x.y version >= 0.294.0 to be installed, which under pre-1.0 semver conventions may include breaking changes in 0.295.0+. | Non-deterministic builds. CI/CD pipeline or fresh installations may pull a breaking version, causing widespread icon rendering failures across every page of the application. This is a deployment risk for any environment that does not use a lockfile or has a stale lockfile. | OPEN
R09-029 | SVP Integrated Production | MEDIUM | Environment Issue | lazyWithRetry | src/utils/lazyWithRetry.js:32 | The lazyWithRetry utility uses a fixed 1-second retry delay (RETRY_DELAY = 1000ms) with no exponential backoff. When a chunk fails to load (e.g., during a deployment with cache invalidation), all 3 retries fire at the same 1-second interval. This provides no relief for transient network issues or CDN propagation delays. Additionally, there is no mechanism to force a page reload when chunk loading ultimately fails after retries -- which is the standard recovery mechanism when a new deployment invalidates old chunk hashes. | 1. Deploy a new version of the application that changes chunk hashes. 2. A user with the old version cached navigates to a lazy-loaded route. 3. The old chunk URL 404s. 4. lazyWithRetry retries 3 times at 1-second intervals. 5. All retries fail because the old chunk no longer exists. 6. User sees the ErrorBoundary fallback with no automatic recovery. | Retry logic should use exponential backoff (e.g., 1s, 2s, 4s). After all retries fail for a ChunkLoadError, the utility should trigger a hard page reload (window.location.reload()) to fetch the updated HTML with new chunk references. This is the standard pattern for handling chunk loading failures after deployments. | Fixed 1s retry delay with no backoff. No page reload fallback. After 3 failed retries, the error propagates to ErrorBoundary and the user is stuck. | During deployments, users with stale cached HTML will encounter chunk loading failures that never self-heal. They must manually refresh the page to recover, leading to support tickets and user frustration. This is especially impactful for single-page apps where users may keep tabs open for extended periods. | OPEN
R09-030 | SVP Integrated Production | MEDIUM | Monitoring Gap | ReadabilityShareView | src/components/readability/ReadabilityShareView.jsx:98 | The ReadabilityShareView is a public-facing page (no auth required) that loads shared analysis reports. When PDF export fails on this public page, the error is only logged to console.error (line 98). There is no user-facing error notification (no toast, no error state) and no monitoring/analytics event. Since this is a public page used for sharing reports with clients and stakeholders, failures here have direct business impact but zero visibility. | 1. Open a shared readability analysis via its public URL. 2. Click 'Download PDF Report'. 3. Simulate a PDF generation failure (e.g., network error, missing fonts). 4. Observe that the error is logged to console.error but no toast or error message is shown to the user. | PDF export failures on the shared view should show a user-facing error message (toast or inline alert). The failure should also be tracked via analytics/monitoring since this is a public-facing feature that reflects on the platform's credibility. | console.error is called but no user-visible feedback is provided. The user clicks the button, sees a loading state, and then nothing happens -- the button returns to its idle state with no indication of failure. | Clients and stakeholders attempting to download PDF reports from shared links experience silent failures, damaging the platform's professional credibility. No monitoring means the team cannot track how often this occurs. | OPEN
R09-031 | SVP Integrated Production | MEDIUM | Caching Gap | storageHelpers | src/utils/storageHelpers.js:67 | When localStorage quota is exceeded (QuotaExceededError), the recovery strategy is to remove STORAGE_KEYS.RECENT_ACTIVITY and retry the write. This approach has several issues: (1) It only evicts one specific key, ignoring potentially larger data stores like ITEM_TIMELINE_DATA or TIME_ENTRIES. (2) It does not assess which key is consuming the most space before evicting. (3) The checkStorageUsage function exists but is never called during quota recovery to make an informed eviction decision. (4) There is no proactive quota management -- the system only reacts after writes fail, by which point user data may already be lost. | 1. Fill localStorage near its limit using the application (many projects, time entries, timeline data). 2. Attempt to save a new filter preset or time entry. 3. Observe the QuotaExceededError handler at line 67. 4. Note that it blindly removes RECENT_ACTIVITY regardless of whether that frees enough space. | The quota recovery strategy should: (1) Call checkStorageUsage() to identify the largest stored items. (2) Evict the least-critical or largest items first. (3) Implement LRU eviction for timeline data. (4) Proactively warn users when approaching quota limits. (5) Consider compressing stored data. | Only RECENT_ACTIVITY is evicted. If that key is small or empty, the retry still fails. No intelligent eviction strategy exists despite checkStorageUsage being available. | Power users with many projects may hit storage quota limits and experience data loss or persistent write failures. Critical data (timeline, time entries) may be silently unwritable while less important data remains in storage. | OPEN
R09-032 | SVP Integrated Production | MEDIUM | Caching Gap | ReadabilityInputScreen | src/components/readability/ReadabilityInputScreen.jsx:292 | The first-use onboarding callout directly accesses localStorage.getItem('readability-onboarded') during render without using the storageHelpers utility and without try/catch error handling. If localStorage is unavailable (private browsing in some browsers, storage quota exceeded, or SSR context), this will throw an unhandled exception during render. Additionally, the key 'readability-onboarded' is not registered in STORAGE_KEYS in storageHelpers.js, bypassing the centralized storage management, quota tracking, and export/import functionality. | 1. Open ReadabilityInputScreen in a browser with localStorage disabled or in an incognito window with storage restrictions. 2. Observe that the component may throw during render on line 292. 3. Search STORAGE_KEYS in storageHelpers.js and confirm 'readability-onboarded' is not registered. | The localStorage access should use the getStorageItem/setStorageItem helpers from storageHelpers.js with proper error handling. The key should be registered in STORAGE_KEYS for centralized management and storage quota tracking. | Raw localStorage.getItem/setItem is used without try/catch, bypassing the centralized storage system. The key is untracked by the storage quota monitoring system. | Potential render crash in environments where localStorage is unavailable. The onboarding state is invisible to the storage export/import, quota monitoring, and data cleanup features, creating inconsistent behavior during data migration or backup/restore. | OPEN
R09-033 | SVP Integrated Production | LOW | Error Logging | useCustomChecklistItems | src/hooks/useCustomChecklistItems.js:39 | The Firestore onSnapshot listener in useCustomChecklistItems does not handle errors via the onSnapshot error callback. The onSnapshot function accepts an optional error handler as its third argument (or via the observer object), but here only the success callback is provided. If the Firestore subscription encounters a permission error, network disconnection, or quota limit, the error will be unhandled and the loading state will remain true indefinitely, leaving users in a perpetual loading state. | 1. Create a project with custom checklist items. 2. Simulate a Firestore permission change (e.g., modify security rules to deny reads). 3. Navigate to the checklist page with custom items. 4. Observe that the component shows a loading state indefinitely with no error message. | onSnapshot should include an error callback: onSnapshot(q, successCallback, errorCallback) that sets loading to false and surfaces the error to the user. | Only the success callback is provided to onSnapshot. Firestore errors result in an infinite loading state with no error handling. | Users may encounter a perpetual loading spinner with no way to recover when Firestore subscription errors occur. No diagnostic information is available for troubleshooting. | OPEN
R09-034 | SVP Integrated Production | LOW | Build Issue | ReportBuilderPage | src/components/reports/ReportBuilderPage.jsx:362 | The HTML export function in ReportBuilderPage constructs an HTML string using template literals with unsanitized user input (reportName). The report name is interpolated directly into the HTML title tag and h1 element without HTML entity encoding. If a user enters a report name containing HTML special characters (e.g., '<script>alert(1)</script>'), the exported HTML file will contain executable scripts. While this is a downloaded file (not served from the application), it could be exploited if the exported HTML is hosted on a web server. | 1. In the Report Builder, set report name to '<img src=x onerror=alert(1)>'. 2. Click Export > Export as HTML. 3. Open the exported HTML file in a browser. 4. Observe that the injected HTML is rendered/executed. | User-supplied strings interpolated into HTML templates should be HTML-entity-encoded to prevent XSS in exported files. | reportName is interpolated directly into the HTML template string without any sanitization or encoding. | While limited to exported files (not the application itself), if exported HTML reports are shared or hosted, they could execute arbitrary scripts. This is a secondary risk but worth addressing for defense in depth. | OPEN
R09-035 | SVP Integrated Production | LOW | Monitoring Gap | FeedbackWidget | src/components/shared/FeedbackWidget.jsx:83 | The FeedbackWidget catches submission errors with an empty catch block that only shows a toast message ('Failed to submit feedback. Please try again.'). There is no console.error, no error logging, and no monitoring event. For a feature specifically designed to collect user feedback (including bug reports), the irony is that bug report submission failures themselves are completely invisible to the team. Additionally, the error object is not logged, so there is no way to distinguish between network failures, Firestore permission issues, or quota limits. | 1. Open the Feedback Widget. 2. Fill in feedback and click Submit. 3. Simulate a Firestore write failure (network disconnect or permission error). 4. Observe that the toast shows 'Failed to submit feedback' but no error details are logged anywhere. | Feedback submission failures should at minimum log the error to console.error with the error object. Ideally, failed feedback submissions should be queued in localStorage for retry, or logged to an alternative endpoint. | The catch block shows a toast but discards the error object entirely. No logging, no retry, no monitoring. | User bug reports and feedback may be silently lost during outages. The team has no visibility into feedback submission failure rates, which is especially problematic for a feature that is the primary user-to-team communication channel. | OPEN
R09-036 | SVP Integrated Production | CRITICAL | Environment Issue | Firebase Configuration | src/lib/firebase.js:7 | Firebase initialization has no validation or fallback when required environment variables are missing. If any VITE_FIREBASE_* variable is undefined, initializeApp() will be called with undefined values, producing a cryptic Firebase error at runtime rather than a clear startup diagnostic. Unlike the AI services which check for config presence, firebase.js blindly passes import.meta.env values without any guard. | 1. Remove or leave blank any VITE_FIREBASE_* variable from the .env file. 2. Run 'npm run build && npm run preview'. 3. Open the application in a browser. | The application should detect missing Firebase configuration at startup and display a clear error message indicating which environment variables are missing, preventing a confusing runtime crash. | Firebase SDK throws an opaque 'FirebaseError: Firebase: Error (auth/invalid-api-key)' or similar runtime error that is difficult to diagnose, especially in production where the .env file may not be properly configured during deployment. | Complete application failure in any deployment environment where Firebase variables are not configured. New developers and CI/CD pipelines may waste significant time debugging. In production, the entire application is non-functional with no actionable error. | OPEN
R09-037 | SVP Integrated Production | CRITICAL | Deploy Risk | AI Suggestion Service | src/lib/ai/suggestionService.js:17 | The VITE_CLAUDE_API_KEY environment variable is exposed in client-side JavaScript bundles. While the suggestionService.js blocks direct API access in production (line 26-31), the schemaGeneratorService.js (line 32) and imageAltService.js (line 32) and aiSuggestionService.js (line 19) do NOT block direct API key usage in production builds. If VITE_CLAUDE_API_KEY is set during a production build, these services will embed and use the API key directly from the browser, exposing it in network requests and the JS bundle. | 1. Set VITE_CLAUDE_API_KEY in .env alongside VITE_AI_PROXY_URL. 2. Run 'npm run build'. 3. Inspect the built JS chunks for the API key string. 4. In schemaGeneratorService.js, imageAltService.js, and aiSuggestionService.js, note that getApiConfig() returns the apiKey without blocking production usage. | All AI service modules should consistently block direct API key usage in production builds, as suggestionService.js does. The API key should never be embedded in production bundles. | schemaGeneratorService.js, imageAltService.js, and metaGeneratorService.js allow direct API key usage in production without the production guard that exists in suggestionService.js. The aiSuggestionService.js only logs a console.warn but does not block it. | API key exposure in production bundles creates a critical security risk. Malicious actors can extract the key from browser DevTools and incur unlimited API charges or abuse the key for unauthorized purposes. | OPEN
R09-038 | SVP Integrated Production | HIGH | Bundle Size | Unified Export Service | src/lib/unifiedExportService.js:6 | unifiedExportService.js statically imports jsPDF, jspdf-autotable, ExcelJS, and JSZip at the top level (lines 6-9). These are very large libraries (jsPDF ~300KB, ExcelJS ~1MB, JSZip ~100KB minified). Unlike useReadabilityExport.js which uses dynamic import() for jsPDF (line 97), unifiedExportService.js forces all these heavy libraries into the main bundle or a shared chunk, defeating the manual chunk splitting configured in vite.config.js. | 1. Run 'npm run build'. 2. Analyze the output bundle sizes. 3. Note that jsPDF, ExcelJS, and JSZip are included in whatever chunk imports unifiedExportService.js. 4. Compare with useReadabilityExport.js which dynamically imports jsPDF. | Heavy export libraries (jsPDF, ExcelJS, JSZip) should be dynamically imported only when export functionality is actually used, keeping the initial bundle small. | Static imports of jsPDF, ExcelJS, and JSZip in unifiedExportService.js cause these large libraries to be bundled eagerly. Any component importing unifiedExportService pulls in ~1.4MB of library code regardless of whether export is used. | Significantly increased initial page load time and bundle size. Users who never use export features still download over 1MB of unnecessary JavaScript, degrading Core Web Vitals (LCP, TBT) and mobile performance. | OPEN
R09-039 | SVP Integrated Production | HIGH | Bundle Size | PDF Generator | src/lib/pdfGenerator.js:7 | pdfGenerator.js statically imports jsPDF and jspdf-autotable at the top level (lines 7-8), similar to unifiedExportService.js. Additionally, excelExport.js (line 1) statically imports ExcelJS. These static imports cause the vendor libraries to be included in eagerly-loaded chunks even though they are only needed when a user explicitly requests a PDF or Excel export. | 1. Run 'npm run build'. 2. Check the generated chunk sizes. 3. Trace which chunks include jsPDF and ExcelJS due to static imports from pdfGenerator.js and excelExport.js. | Export-related heavy dependencies should use dynamic import() to enable proper code splitting, consistent with the pattern already used in useReadabilityExport.js. | jsPDF (~300KB) and ExcelJS (~1MB) are statically imported, forcing them into chunks that load before the user ever requests an export. | Increased bundle sizes hurt page load performance. The vite.config.js manualChunks configuration for vendor-exceljs and vendor-jspdf tries to isolate these, but static imports from multiple entry points may cause them to be loaded unnecessarily early. | OPEN
R09-040 | SVP Integrated Production | HIGH | Error Logging | Notification Service | src/hooks/useNotifications.js:98 | The createNotification function (lines 86-101) silently swallows all errors in its catch block with an empty body and a comment 'Silently fail - notification creation is non-critical'. Similarly, markAsRead (line 55) silently swallows errors. While individual notification failures may not be critical, having zero error logging means there is no way to detect systematic Firestore write failures, permission issues, or connectivity problems that could indicate broader infrastructure issues. | 1. Simulate a Firestore write failure (e.g., invalid permissions or network disconnection). 2. Trigger any action that calls createNotification(). 3. Check browser console and any monitoring tools for error traces. | At minimum, errors should be logged (e.g., console.error) so they appear in browser error monitoring tools. Ideally, failed notifications should be queued for retry or reported to an error tracking service. | All errors are completely swallowed with no logging, no retry, and no monitoring visibility. Systematic failures go entirely undetected. | Operations teams cannot diagnose notification delivery failures. If Firestore permissions are misconfigured or the database is degraded, no alerts or logs are generated, leading to prolonged silent failures affecting user experience. | OPEN
R09-041 | SVP Integrated Production | HIGH | Monitoring Gap | Lazy Load Retry | src/utils/lazyWithRetry.js:37 | The lazyWithRetry utility only logs chunk loading failures in development mode (line 37: if (import.meta.env.DEV)). In production, when a chunk fails to load after 3 retries, the error is re-thrown as a generic message with no telemetry, no error reporting service call, and no metrics emission. This means production chunk loading failures — which indicate CDN issues, cache invalidation problems, or deployment mismatches — are completely invisible to operations teams. | 1. Deploy the application. 2. Simulate a chunk loading failure (e.g., delete a chunk file from the CDN). 3. Navigate to a lazy-loaded route. 4. Observe that after 3 retries, the error boundary catches the error but no telemetry is sent to any monitoring service. | Production chunk loading failures should be reported to an error monitoring service (e.g., Sentry, Datadog) with the module name, retry count, and error details so operations can detect and respond to deployment issues. | In production, chunk load failures are silently re-thrown with only a user-facing message. No telemetry, metrics, or external error reports are generated. | Deployment failures or CDN issues that cause chunk loading errors go undetected in production. Users see error boundaries but the engineering team has no visibility into the frequency or scope of these failures. | OPEN
R09-042 | SVP Integrated Production | HIGH | Caching Gap | Analysis Cache | src/lib/readability/utils/analysisCache.js:17 | The content hash function hashContent() only processes the first 50,000 characters of the HTML content (line 18: Math.min(content.length, 50000)). For large pages exceeding 50KB of HTML, two different pages with identical first 50K characters but different subsequent content will produce the same hash, causing incorrect cache hits and returning stale or wrong analysis results to the user. | 1. Analyze a URL with a page whose HTML exceeds 50,000 characters. 2. Modify content after the 50,000th character (e.g., different footer, different article content). 3. Re-analyze the same URL. 4. Observe that the cache returns the old result because the hash only covers the first 50K characters. | The hash function should process the entire content or use a sampling strategy that covers both the beginning and end of the document to detect changes anywhere in the content. | hashContent() truncates at 50,000 characters, creating hash collisions for pages where changes occur beyond that boundary. | Users receive incorrect cached analysis results for large pages, leading to wrong readability scores and recommendations. This is particularly problematic for e-commerce pages, long-form content, and pages with dynamic content sections near the end. | OPEN
R09-043 | SVP Integrated Production | MEDIUM | Build Issue | Vite Configuration | vite.config.js:25 | The Vite build configuration sets chunkSizeWarningLimit to 600KB (line 25), which suppresses warnings for chunks up to 600KB. The default Vite limit is 500KB, and the stated reason is 'since we have lazy loading'. However, the presence of static imports in unifiedExportService.js and pdfGenerator.js means some chunks may exceed even this raised limit. Increasing the warning limit masks genuine bundle size regressions instead of addressing the root cause (missing dynamic imports). | 1. Review vite.config.js build configuration. 2. Run 'npm run build' and check for any chunk size warnings. 3. Note that raising the limit to 600KB hides potential issues rather than solving them. | The chunk size warning limit should remain at the default (500KB) or lower. Any chunks exceeding the limit should be addressed through proper code splitting and dynamic imports rather than suppressing the warning. | chunkSizeWarningLimit is raised to 600KB, which suppresses legitimate warnings about oversized chunks that could degrade performance. | Bundle size regressions go unnoticed during development and CI. Over time, chunk sizes may creep upward without any build-time alert, gradually degrading application load performance. | OPEN
R09-044 | SVP Integrated Production | MEDIUM | Deploy Risk | Schema Generator Service | src/lib/schema-generator/schemaGeneratorService.js:38 | Unlike suggestionService.js which throws an error when API key is used in production, schemaGeneratorService.js getApiConfig() (line 30-43) returns { useProxy: false, apiKey } without any production guard. If VITE_CLAUDE_API_KEY is present in the environment during a production build, the service will use direct browser-to-API calls with the header 'anthropic-dangerous-direct-browser-access: true' (line 291). This inconsistency means some AI features are properly secured while others are not. | 1. Set both VITE_AI_PROXY_URL and VITE_CLAUDE_API_KEY in the environment. 2. Remove VITE_AI_PROXY_URL to simulate a misconfiguration. 3. Build for production. 4. Use the schema generator feature. 5. Observe that the API key is sent directly from the browser. | schemaGeneratorService.js should block direct API key usage in production builds, consistent with the pattern in suggestionService.js. | schemaGeneratorService.js allows direct API key usage in production without any guard, enabling insecure browser-to-API communication. | Inconsistent security posture across AI services. A misconfiguration or intentional decision to set VITE_CLAUDE_API_KEY results in API key exposure for schema generation, image alt generation, and meta generation features. | OPEN
R09-045 | SVP Integrated Production | MEDIUM | Error Logging | Storage Helpers | src/utils/storageHelpers.js:48 | All error handling in storageHelpers.js relies exclusively on console.error/console.warn calls (lines 48, 64, 68, 75, 90, 314, 362). There is no integration with any structured logging or error monitoring service. Additionally, the importAllData function (line 353) accepts arbitrary JSON data without any schema validation, version checking, or sanitization — it blindly writes to all storage keys, which could corrupt application state if malformed data is imported. | 1. Call importAllData() with a JSON object containing invalid or malformed data for one of the storage keys. 2. Observe that the data is written without validation. 3. Navigate to features that depend on that storage key. 4. Observe broken behavior due to corrupted data. | importAllData should validate the schema and version of imported data before writing. Error logging should integrate with a monitoring service rather than relying solely on console output. | importAllData writes arbitrary data to localStorage without validation. All error logging goes only to console, which is not captured by any production monitoring. | Users can corrupt their local application state by importing malformed backup files. Error conditions in localStorage operations are invisible in production monitoring, making it impossible to diagnose user-reported issues related to data persistence. | OPEN
R09-046 | SVP Integrated Production | MEDIUM | Monitoring Gap | AI Analyzer | src/lib/readability/aiAnalyzer.js:54 | In aiAnalyzer.js, when the caller provides an AbortSignal via options.signal (line 54), the code creates a NEW AbortController and its own signal but then uses 'const signal = options.signal ¦¦ controller.signal'. This means if the caller passes a signal, the internal timeout controller's abort will never trigger because the fetch uses the caller's signal instead. The 120-second timeout (line 10) is effectively bypassed whenever options.signal is provided, which is the normal usage path from useReadabilityAnalysis. | 1. Call analyzeWithAI() from useReadabilityAnalysis which passes options.signal. 2. Make the AI proxy take longer than 120 seconds to respond. 3. Observe that the internal 120s timeout does not abort the request because the caller's signal is used instead. | The timeout should work in conjunction with the caller's signal. Both should be able to abort the request — the caller for cancellation, the internal timer for timeout protection. | The internal timeout controller is created but its signal is never used when options.signal is provided. The 120-second timeout is silently bypassed, and the request can hang indefinitely until the caller aborts or the browser times out. | Users may experience indefinitely hanging analysis requests if the AI proxy is slow or unresponsive, with no timeout protection. This wastes server resources and degrades user experience. | OPEN
R09-047 | SVP Integrated Production | MEDIUM | Dependency Risk | Package Dependencies | package.json:23 | Several dependencies use caret (^) version ranges, which means minor and patch versions can change between installs. Critical dependencies like firebase (^12.7.0), jspdf (^4.0.0), and exceljs (^4.4.0) could receive breaking updates within their major version. Additionally, there is no package-lock.json enforcement or lockfile integrity check in the build scripts, and the dependency count is large (17 runtime dependencies) with no evidence of periodic audit. | 1. Review package.json dependencies. 2. Run 'npm audit' to check for known vulnerabilities. 3. Note that caret ranges allow minor version drift. 4. Check if a lockfile is committed and if CI enforces 'npm ci' over 'npm install'. | Production builds should use exact versions or a lockfile with integrity checks. The build script should use 'npm ci' to ensure reproducible builds. Regular dependency audits should be part of the CI pipeline. | All dependencies use caret ranges. Build script uses 'vite build' without any lockfile integrity enforcement. No audit script is defined in package.json scripts. | Non-reproducible builds across environments. Different developers or CI runs may get different dependency versions, leading to inconsistent behavior and hard-to-diagnose bugs. Undetected dependency vulnerabilities may persist. | OPEN
R09-048 | SVP Integrated Production | MEDIUM | Caching Gap | Analysis Cache | src/lib/readability/utils/analysisCache.js:107 | The analysis cache stores potentially large analysis result objects in localStorage (line 107), but there is no size check before writing. Each cached analysis contains checkResults, recommendations, llmExtractions, and aiAssessment data that could be several hundred KB when serialized to JSON. With MAX_CACHE_ENTRIES set to 20 (line 9), the cache could consume several MB of the ~5MB localStorage quota, directly competing with the storageHelpers.js STORAGE_KEYS data and potentially causing QuotaExceededError across the application. | 1. Run 20 different URL analyses to fill the cache. 2. Check localStorage usage via storageHelpers.checkStorageUsage(). 3. Observe that the readability cache entries are not counted by checkStorageUsage() because they use a different key prefix. 4. Attempt to save other data and observe potential quota exceeded errors. | The analysis cache should coordinate with the storage management system in storageHelpers.js. Cache entries should have a size limit, and the total cache size should be bounded. checkStorageUsage() should account for readability cache entries. | The analysis cache operates independently from storageHelpers.js storage management. It has no per-entry size limit and does not integrate with checkStorageUsage(), creating an invisible storage consumer that can exhaust the localStorage quota. | Users with active readability analysis usage may experience data loss in other application features (timeline data, filter presets, time entries) when localStorage fills up, with no advance warning from the storage monitoring system. | OPEN
R09-049 | SVP Integrated Production | MEDIUM | Monitoring Gap | Export History | src/hooks/useExportHistory.js:110 | The logExport function (line 100-113) catches errors but only logs them to console.error and returns null. There is no metric tracking for export success/failure rates, no tracking of export durations, and no monitoring of which export types are most used. The deleteExport function (line 117-123) similarly only logs errors to console. For a business-critical feature like report generation and export, this lack of telemetry makes it impossible to understand export reliability and usage patterns. | 1. Trigger an export action. 2. Simulate a Firestore write failure. 3. Check for any monitoring or metrics that capture the failure. 4. Review the codebase for any export analytics or success rate tracking. | Export operations should emit success/failure metrics to a monitoring service. Export type, format, duration, and file size should be tracked for operational visibility. | Export failures are logged only to console.error. No metrics, analytics, or structured telemetry exists for export operations. | Product and operations teams have no visibility into export reliability, usage patterns, or failure rates. Systematic export failures affecting users go undetected until users manually report issues. | OPEN
R09-050 | SVP Integrated Production | LOW | Code Splitting | Vite Manual Chunks | vite.config.js:20 | The manualChunks configuration in vite.config.js includes 'htmlparser2' and 'franc' in the 'vendor-readability' chunk (line 20), but these libraries are used exclusively by the readability analysis feature. Grouping them with jszip (which is used by both audit export and readability export) into a single vendor chunk means that navigating to any feature that uses jszip will also load htmlparser2 and franc, even if readability analysis is never used. | 1. Navigate to the audit export feature which uses jszip. 2. Check the network panel for loaded chunks. 3. Observe that htmlparser2 and franc are loaded alongside jszip even though they are not needed for audit export. | htmlparser2 and franc should be in a separate chunk from jszip, or the readability-specific libraries should be loaded only when the readability feature is accessed. | htmlparser2, franc, and jszip are bundled together in vendor-readability, causing unnecessary library loading for non-readability features that only need jszip. | Minor increase in loaded JavaScript for users accessing audit features. Suboptimal code splitting reduces the effectiveness of lazy loading for the readability feature. | OPEN
R09-051 | SVP Integrated Production | LOW | Error Logging | useProjects Hook | src/hooks/useProjects.js:90 | The getProject function (lines 90-97) has no try-catch error handling. If the Firestore getDoc call fails due to a network error, permission issue, or invalid projectId, the error will bubble up as an unhandled promise rejection to the calling component. All other CRUD operations in the same hook (createProject, updateProject, deleteProject) have try-catch blocks, making this an inconsistent oversight. | 1. Call getProject() with an invalid or inaccessible project ID. 2. Observe that the unhandled error propagates to the component. 3. Compare with createProject/updateProject/deleteProject which all have error handling. | getProject should have consistent error handling with try-catch, error logging, and a user-friendly error message, matching the pattern of the other CRUD operations in the same hook. | getProject has no error handling. A Firestore error results in an unhandled promise rejection. | Components calling getProject may crash without a helpful error message if the Firestore call fails, degrading user experience when viewing project details under degraded network conditions. | OPEN