## Role 1 - Lead React Developer
Bug ID | Role | Severity | Category | Component | File:Line | Description | Steps to Reproduce | Expected Behavior | Actual Behavior | Impact | Status
R01-001 | Lead React Developer | MEDIUM | Memory Leak | FixSuggestionsPanel | src/components/accessibility/FixSuggestionsPanel.jsx:740 | setTimeout in handleCopy never cleared on unmount. If component unmounts before 2s timer completes, setCopiedSection will be called on unmounted component. | 1. Click copy button in FixSuggestionsPanel 2. Close the panel within 2 seconds 3. Observe console warning about state update on unmounted component | Timer should be cleaned up when component unmounts via useEffect cleanup or useRef. | setTimeout at line 740 is never cleared, causing potential state update on unmounted component. | React warning about state update on unmounted component; potential memory leak in rapid open/close scenarios. | OPEN
R01-002 | Lead React Developer | MEDIUM | React Anti-Pattern | VPATReportGenerator | src/components/accessibility/VPATReportGenerator.jsx:99 | Unused state variables _showPreview and _setShowPreview declared with eslint-disable. The Preview button at line 427-429 has no onClick handler, making it non-functional. | 1. Open VPATReportGenerator 2. Click the Preview button in the footer | Preview button should toggle a preview view of the VPAT report. | Preview button has no onClick handler and the state variables for preview are unused (prefixed with underscores). | Dead code and non-functional UI element; users cannot preview their VPAT report before exporting. | OPEN
R01-003 | Lead React Developer | HIGH | Missing Error Handling | AccessibilityDashboard | src/components/accessibility/dashboard/AccessibilityDashboard.jsx:536 | new URL(page.address) at line 536 will throw if page.address is not a valid URL, crashing the component inside a render path without try-catch. | 1. Process a crawl export containing relative URLs or malformed addresses 2. Navigate to the Overview tab 3. Component crashes with TypeError | Invalid URLs should be handled gracefully with a fallback display. | Unhandled URL constructor throws TypeError, crashing the entire dashboard via React error boundary. | Complete dashboard crash if any page address in worstPages is not a valid absolute URL. | OPEN
R01-004 | Lead React Developer | LOW | Performance Bug | AccessibilityDashboard | src/components/accessibility/dashboard/AccessibilityDashboard.jsx:146 | handleExportPDF, handleExportExcel, and handleExportVPAT functions are not wrapped in useCallback despite referencing stable dependencies. These get recreated on every render. | 1. Open AccessibilityDashboard 2. Interact with any filter or state change 3. All export handler functions are recreated | Export handlers should be memoized with useCallback to prevent unnecessary recreations. | Functions are recreated on every render, though impact is minimal since they are not passed as props to memoized children. | Minor performance concern; unnecessary function recreations on each render cycle. | OPEN
R01-005 | Lead React Developer | HIGH | State Bug | AuditLogViewer | src/components/admin/AuditLogViewer.jsx:261 | Refresh button sets loading to true but never triggers data re-fetch. The useEffect at line 93 depends only on dateRange, but the Refresh button only calls setLoading(true) without changing dateRange. | 1. Open AuditLogViewer 2. Click the Refresh button 3. Observe that loading spinner appears but never completes | Refresh button should re-trigger the data fetch and eventually set loading to false. | Loading state is set to true but fetchLogs is never re-invoked, leaving the component in a permanent loading state. | Users clicking Refresh will see an infinite loading spinner with no way to recover except page reload. | OPEN
R01-006 | Lead React Developer | MEDIUM | React Anti-Pattern | AuditLogViewer | src/components/admin/AuditLogViewer.jsx:428 | Dynamic Tailwind CSS class names constructed via string interpolation (e.g., bg-${color}-100) will not work. Tailwind purges classes at build time and cannot detect dynamically composed class names. | 1. Open AuditLogViewer with action log entries 2. Observe that action badges have no background colors applied | Action type badges should display appropriate colors (emerald for Create, blue for Read, etc.). | Dynamic class interpolation produces class names that are purged by Tailwind CSS at build time, resulting in unstyled elements. | Visual degradation; action type badges will have no background or text colors in production builds. | OPEN
R01-007 | Lead React Developer | HIGH | State Bug | UsageAnalyticsDashboard | src/components/admin/UsageAnalyticsDashboard.jsx:259 | Same Refresh button bug as AuditLogViewer: setLoading(true) without triggering re-fetch. The useEffect depends on [dateRange, dateRangeConfig], but clicking Refresh only sets loading state without changing dependencies. | 1. Open UsageAnalyticsDashboard 2. Click the Refresh button 3. Component stays in loading state indefinitely | Refresh should re-trigger the fetchStats function. | Loading state is set to true but fetchStats is never re-invoked. Component remains in permanent loading state. | Permanent loading spinner after clicking Refresh; requires page reload to recover. | OPEN
R01-008 | Lead React Developer | CRITICAL | Race Condition | BatchAuditPanel | src/components/audit/BatchAuditPanel.jsx:314 | Stale closure bug in runBatchAudit: the for-loop checks 'if (!isRunning) break;' at line 314, but isRunning is captured by closure at the time runBatchAudit starts. It will always be the initial value (true, set at line 309), so the pause functionality (pauseAudit at line 385) will never actually stop the loop. | 1. Add multiple URLs to batch audit 2. Click Start Batch Audit 3. Click Pause while audit is running 4. Observe that the audit continues despite isRunning being set to false | Clicking Pause should stop the batch audit loop at the next iteration. | The isRunning check inside the async for-loop references the stale closure value, so the loop never breaks. Pause button appears to work (state changes) but the loop continues. | Pause functionality is completely broken. Users cannot stop a running batch audit. The loop will process all URLs regardless of user action. | OPEN
R01-009 | Lead React Developer | MEDIUM | React Anti-Pattern | ScheduledAuditsPanel | src/components/audit/ScheduledAuditsPanel.jsx:419 | Multiple dynamic Tailwind CSS class names constructed via string interpolation throughout the component (e.g., bg-${scoreColor}-100, text-${scoreColor}-600, bg-${trend.color}-100). These will be purged by Tailwind at build time. | 1. Create a scheduled audit with history 2. View the audit score badge and trend indicator 3. Observe missing background and text colors | Score badges and trend indicators should show proper emerald/amber/red colors. | Dynamic class construction produces class names that Tailwind cannot detect during build-time purge, resulting in unstyled elements. | Score badges, trend indicators, and history chart bars will have no colors in production. Widespread visual degradation. | OPEN
R01-010 | Lead React Developer | MEDIUM | Hook Misuse | ScheduledAuditsPanel | src/components/audit/ScheduledAuditsPanel.jsx:790 | The useEffect for checking schedule conflicts has eslint-disable-next-line for exhaustive deps. checkConflicts function is defined inside the component body and not memoized, but is excluded from the dependency array. More importantly, checkConflicts could reference stale formData values. | 1. Open AuditScheduleFormModal 2. Change the time to a peak hours value 3. Conflicts may not update correctly due to stale closure | checkConflicts should be either memoized with useCallback or included as a dependency. | The eslint-disable hides the dependency warning. checkConflicts references formData but is not listed as a dependency, potentially showing stale conflict data. | Schedule conflict warnings may not appear or disappear correctly when form data changes. | OPEN
R01-011 | Lead React Developer | HIGH | React Anti-Pattern | ReadabilityCheckItem | src/components/readability/ReadabilityCheckItem.jsx:154 | Uses dangerouslySetInnerHTML to render jargon-annotated text, creating a potential XSS vector. The annotateJargon function injects raw HTML from check.title/check.name which could contain user-supplied content. | 1. Provide a check object with a title containing malicious HTML like '<img src=x onerror=alert(1)>' 2. Render ReadabilityCheckItem with this check 3. Observe the injected HTML is rendered unsanitized via dangerouslySetInnerHTML | User-supplied content should be escaped or rendered using safe React elements, not raw HTML injection. | Raw HTML from annotateJargon() is injected via dangerouslySetInnerHTML, allowing potential script injection if check titles contain untrusted content. | Any user or API response that sets check.title with malicious content could execute arbitrary JavaScript in the browser, affecting all users viewing readability results. | OPEN
R01-012 | Lead React Developer | HIGH | Hook Misuse | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:57 | The useEffect that loads trend data calls historyHook.getTrendData().then() but historyHook is omitted from the dependency array (suppressed with eslint-disable). If historyHook reference changes, the effect uses a stale closure over an old hook instance. | 1. Open ReadabilityDashboard with an analysis 2. The useEffect fires on mount with initial historyHook 3. If historyHook re-creates (e.g., parent re-render with new hook reference), the effect does not re-run 4. Trend data may become stale or reference an unmounted hook | The useEffect should include historyHook in the dependency array or use a stable ref, and handle the promise rejection. | historyHook is excluded from dependencies via eslint-disable comment, causing potential stale closures. The .then() chain also has no .catch() for error handling. | Users may see stale trend data. Unhandled promise rejection could cause console errors in production. | OPEN
R01-013 | Lead React Developer | MEDIUM | Missing Error Handling | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:57 | The getTrendData promise chain lacks a .catch() handler. If the async call fails (e.g., network error), the promise rejection goes unhandled. | 1. Open ReadabilityDashboard while offline or with a failing API 2. The historyHook.getTrendData() promise rejects 3. No .catch() is present to handle the error | A .catch() handler should be present to gracefully handle errors, possibly setting an error state or showing a fallback. | Unhandled promise rejection occurs, potentially crashing in strict mode environments or showing console errors. | Users in unreliable network conditions will see unhandled promise errors; no user feedback about the failure. | OPEN
R01-014 | Lead React Developer | MEDIUM | Performance Bug | ReadabilityCoverageTable | src/components/readability/ReadabilityCoverageTable.jsx:58 | The sortedData computation on lines 58-68 is not wrapped in useMemo. It performs array spread and sort on every render, even when data, sortCol, and sortDir have not changed. | 1. Render ReadabilityCoverageTable with data 2. Any parent re-render triggers this component to re-render 3. Observe that sortedData recomputes (array copy + sort) on every single render | The sorting computation should be memoized with useMemo([data, sortCol, sortDir]) to prevent unnecessary re-computation on every render. | sortedData is computed as a plain variable derived from data, sortCol, and sortDir, causing re-computation on every render regardless of whether those values changed. | Performance degradation with large datasets; unnecessary array sorting on every render cycle. | OPEN
R01-015 | Lead React Developer | MEDIUM | React Anti-Pattern | ReadabilityInputScreen | src/components/readability/ReadabilityInputScreen.jsx:292 | Direct localStorage access during render (!localStorage.getItem('readability-onboarded')) causes SSR incompatibility and will throw a ReferenceError in server-side rendering environments where localStorage is undefined. | 1. Attempt to server-side render the ReadabilityInputScreen component 2. The conditional at line 292 calls localStorage.getItem() during render 3. ReferenceError is thrown because localStorage is not available on the server | localStorage access should be guarded with a typeof window check or moved into a useEffect/useState pattern to avoid SSR crashes. | localStorage is accessed directly during render without any guard, causing crashes in SSR environments. | Breaks server-side rendering; prevents use of SSR frameworks like Next.js; may cause hydration mismatches in universal rendering. | OPEN
R01-016 | Lead React Developer | MEDIUM | State Bug | ReadabilityInputScreen | src/components/readability/ReadabilityInputScreen.jsx:308 | The dismiss button for the onboarding callout calls setActiveTab(activeTab) as a hack to force re-render after writing to localStorage. This does not actually force a re-render since React will bail out when setting state to the same value. | 1. Open ReadabilityInputScreen for the first time (no 'readability-onboarded' in localStorage) 2. Click 'Dismiss' on the onboarding callout 3. localStorage is updated, but setActiveTab(activeTab) sets the same value 4. React bails out of re-render; the callout remains visible | The component should use a state variable to track dismissal (e.g., useState) so that calling the setter triggers a proper re-render. | setActiveTab(activeTab) with the same value does not trigger re-render, so the onboarding callout persists until page navigation. | Users cannot dismiss the onboarding callout on first interaction; poor UX for first-time users. | OPEN
R01-017 | Lead React Developer | MEDIUM | Performance Bug | ReadabilityIssuesTable | src/components/readability/ReadabilityIssuesTable.jsx:159 | The SortHeader component is defined as a function inside the render body of ReadabilityIssuesTable. This means it is recreated on every render, causing React to unmount and remount all SortHeader instances instead of reconciling them. | 1. Render ReadabilityIssuesTable with check results 2. Interact with any filter or sort control 3. Observe that SortHeader is redefined as a new function on each render 4. React treats each render's SortHeader as a new component type, unmounting/remounting all headers | SortHeader should be defined outside the component body or memoized so React can properly reconcile it across renders. | SortHeader is redefined inside the render function on every render, causing unnecessary unmount/remount cycles for all table headers. | Causes unnecessary DOM thrashing on every filter or sort interaction; hurts performance with larger datasets. | OPEN
R01-018 | Lead React Developer | HIGH | Race Condition | ReadabilityPage | src/components/readability/ReadabilityPage.jsx:83 | The useEffect that loads an analysis by ID (lines 80-96) fires an async operation but does not track whether the component is still mounted or whether the analysisId has changed. If a user navigates between analyses rapidly, earlier promises may resolve after later ones, overwriting the correct result with stale data. | 1. Navigate to /app/readability/analysis-1 2. Quickly navigate to /app/readability/analysis-2 before analysis-1 finishes loading 3. analysis-1 resolves after analysis-2 4. setLoadedResult(data) from analysis-1 overwrites the correct analysis-2 result | The effect should use an AbortController or a stale-request flag (let cancelled = false) to discard results from outdated requests. | No cancellation mechanism exists; the last-resolving promise wins regardless of which analysisId is current, causing a race condition. | Users may see the wrong analysis results when navigating between analyses quickly, leading to confusion and incorrect data display. | OPEN
R01-019 | Lead React Developer | HIGH | Hook Misuse | ReadabilityPage | src/components/readability/ReadabilityPage.jsx:96 | The useEffect dependency array omits history.getAnalysisById (suppressed with eslint-disable). If the history hook reference changes, the effect uses a stale function reference that may not work correctly. | 1. The history hook re-initializes due to a context change 2. The useEffect still uses the old history.getAnalysisById reference 3. The stale function may reference outdated state or fail silently | Either include the dependency or use a ref to ensure the latest function is always called. | The eslint-disable comment suppresses the warning, but the stale function reference remains a latent bug. | Could cause silent failures when loading existing analyses if the history context re-initializes. | OPEN
R01-020 | Lead React Developer | HIGH | React Anti-Pattern | ReportBuilderPage | src/components/reports/ReportBuilderPage.jsx:362 | The HTML export function embeds reportName directly into an HTML template string without escaping. If the user sets a report name containing HTML tags or script injection payloads, those will be rendered verbatim in the exported HTML file. | 1. Set reportName to '<script>alert(document.cookie)</script>' 2. Click Export as HTML 3. Open the exported HTML file in a browser 4. The script executes in the context of the HTML file | The reportName should be HTML-escaped before being interpolated into the HTML template string. | reportName is interpolated raw into the HTML template on lines 366 and 377, creating an XSS vulnerability in exported files. | Users who open exported HTML files could be vulnerable to XSS attacks if report names are crafted maliciously, especially in team environments where reports are shared. | OPEN
R01-021 | Lead React Developer | MEDIUM | State Bug | ScheduledReportsPanel | src/components/reports/ScheduledReportsPanel.jsx:169 | The toggleSchedule function reads from the stale `schedules` state variable to find the schedule and display the toast message. Because setSchedules is called before the toast, the toast reads the old isActive value (before the toggle), causing the message to display the inverted status. | 1. Create a schedule that is active (isActive: true) 2. Click the Pause button to toggle the schedule 3. setSchedules updates isActive to false 4. The const schedule = schedules.find(s => s.id === id) still references the old state 5. Toast shows 'Schedule activated' instead of 'Schedule paused' | The toast message should reflect the new state. Either compute the new state before calling setSchedules, or read from the updated value. | schedule.isActive reads the pre-toggle value, so the toast message is inverted: it says 'activated' when pausing and 'paused' when activating. | Users receive confusing, incorrect feedback about whether a schedule was paused or activated. | OPEN
R01-022 | Lead React Developer | MEDIUM | State Bug | useChecklist | src/hooks/useChecklist.js:41 | In the toggleItem function, the revert-on-error handler at line 63 uses `completions[itemId]` from the closure captured at call time, not the current state. If multiple toggles happen before the error, the revert value may be incorrect. | 1. Call toggleItem(42) which sets completions[42] = true (optimistic) 2. Before the Firestore update completes, call toggleItem(42) again which sets completions[42] = false 3. The first Firestore call fails 4. The catch handler reverts using !completions[itemId] from the first call's closure, which is !false = true 5. The state is now true, but the second toggle intended it to be false | The revert should use a functional setState that captures the actual current state, or store the previous value before the optimistic update. | The revert uses a stale closure reference to completions[itemId], which may not reflect the latest state after concurrent toggles. | Checklist items may show incorrect completion status after concurrent toggles and a Firestore error, confusing users about task progress. | OPEN
R01-023 | Lead React Developer | MEDIUM | State Bug | useAssignments | src/hooks/useAssignments.js:60 | The assignTask function performs an optimistic state update (line 61) but does not revert the local state if the Firestore update fails. If the server write fails, the UI shows the assignment was made, but it was not persisted. | 1. Call assignTask with a user assignment 2. The local state is immediately updated at line 61 3. The Firestore getDoc or setDoc call fails (e.g., network error) 4. The catch handler logs the error and shows a toast, but does not revert the local state | On Firestore error, the optimistic local state update should be reverted to the previous state so the UI reflects reality. | The local state retains the optimistic update even after Firestore fails, causing the UI to show assignments that do not exist in the database. | Users see phantom task assignments that disappear on page refresh, causing confusion about who is responsible for tasks. | OPEN
R01-024 | Lead React Developer | MEDIUM | State Bug | useCustomChecklistItems | src/hooks/useCustomChecklistItems.js:109 | The toggleComplete callback captures customItems via closure but includes it in its dependency array. The function reads `const item = customItems.find(i => i.id === itemId)` using the stale closure. If the function is called rapidly, it may use an outdated version of customItems. | 1. Toggle a custom item's completion status 2. Rapidly toggle it again before the first Firestore update resolves 3. The second call may read an outdated `customItems` from the closure 4. The completed field is toggled based on stale data | The function should read from a ref or use the Firestore snapshot directly rather than relying on a stale closure over customItems. | toggleComplete uses customItems from its closure, which may be stale during rapid successive calls. | Custom checklist items may have their completion status incorrectly toggled under rapid user interaction. | OPEN
R01-025 | Lead React Developer | LOW | Performance Bug | ReadabilityWeightConfig | src/components/readability/ReadabilityWeightConfig.jsx:35 | The handleChange useCallback depends on localWeights, which means a new function is created every time any slider moves. This defeats the purpose of useCallback since the dependency changes on every interaction. | 1. Render ReadabilityWeightConfig 2. Move any slider to change a weight 3. localWeights changes, causing handleChange to be recreated 4. All slider onChange handlers receive a new function reference on every change | Use a functional setState pattern (setLocalWeights(prev => ({ ...prev, [key]: Number(value) }))) and remove localWeights from the dependency array. | handleChange is recreated on every slider change because localWeights is in the dependency array, even though it could use a functional updater instead. | Minor performance issue; unnecessary function recreations and child re-renders during slider interactions. | OPEN
R01-026 | Lead React Developer | LOW | State Bug | useChecklistTemplates | src/hooks/useChecklistTemplates.js:122 | The incrementUsage callback captures templates via closure. It finds the template and reads template.usageCount to compute the new count. However, if multiple increments happen before Firestore updates, each call reads the same stale usageCount value, losing increments. | 1. Call incrementUsage('template-1') twice in quick succession 2. Both calls read the same templates array from the closure 3. Both compute usageCount + 1 from the same stale value 4. Only one increment is persisted instead of two | Use Firestore's increment() operator or FieldValue.increment(1) to atomically increment the counter server-side. | The increment reads the local stale template.usageCount and writes usageCount + 1, causing lost updates under concurrent calls. | Usage counts for templates may be undercounted, providing inaccurate analytics about which templates are most popular. | OPEN
R01-027 | Lead React Developer | MEDIUM | Prop Issue | ReportWidgetRenderer | src/components/reports/ReportWidgetRenderer.jsx:169 | In the renderArrayChart function, circle elements inside the SVG use the array index as the key (key={i} at line 174). Since chart data can be reordered or filtered, using array index as key can cause incorrect reconciliation and animation glitches. | 1. Render a line/area chart with array data 2. Change the data source or filter the data 3. React reconciles using index-based keys 4. Circle elements may animate from/to wrong positions | Use a stable unique identifier from the data item (e.g., data item name or date) as the key. | Array index is used as the key, which causes React to reuse DOM elements incorrectly when data changes. | Chart animations may glitch and circles may appear to jump to wrong positions when data is updated. | OPEN
R01-028 | Lead React Developer | MEDIUM | Memory Leak | ReadabilityPage | src/components/readability/ReadabilityPage.jsx:58 | The useEffect for keyboard shortcuts adds an event listener on every showShortcuts change and removes it on cleanup. However, during the transition window between cleanup and re-registration, if the component unmounts, there is no guarantee the cleanup runs synchronously. More importantly, the effect registers a new listener every time showShortcuts toggles, creating rapid add/remove cycles that may miss events. | 1. Open ReadabilityPage 2. Rapidly press '?' to toggle shortcuts 3. Each toggle removes and re-adds the keydown listener 4. During rapid toggling, events may be dropped | Register the keyboard listener once and use a ref for showShortcuts to avoid re-registering the listener on every state change. | The keyboard listener is removed and re-added on every showShortcuts toggle, creating a brief window where keyboard events are unhandled. | Users may experience intermittent failure when pressing Escape to close shortcuts overlay during rapid interaction. | OPEN
R01-029 | Lead React Developer | MEDIUM | State Bug | useFavoritesAndRecents | src/hooks/useFavoritesAndRecents.js:66 | addToFavorites, removeFromFavorites, and addToRecents use stale closure values of `favorites` and `recents` state. When these callbacks fire in quick succession, they reference outdated snapshots of the arrays, causing earlier mutations to be overwritten. | 1. Open a page using useFavoritesAndRecents hook. 2. Rapidly click 'Add to Favorites' on two different items in quick succession. 3. Observe that only the second item appears in favorites. | Both items should be added to favorites since each operation should see the latest state. | The second addToFavorites call captures the stale `favorites` array (without the first item), so the first add is lost when saveData is called the second time. | Users who quickly favorite multiple items will lose some favorites. The same issue affects addToRecents at line 103. | OPEN
R01-030 | Lead React Developer | MEDIUM | Missing Error Handling | useNotifications | src/hooks/useNotifications.js:60 | markAllAsRead uses a Firestore writeBatch without checking if the number of unread notifications exceeds the Firestore batch limit of 500 operations. If a user has more than 500 unread notifications, batch.commit() will throw an error. | 1. Accumulate more than 500 unread notifications for a user. 2. Click 'Mark all as read'. 3. Observe an error toast. | All notifications should be marked as read, splitting into multiple batches if necessary. | Firestore throws 'Maximum 500 writes allowed per batch' error and no notifications are marked as read. | Power users or users who haven't cleared notifications for a long time will be unable to mark all as read. | OPEN
R01-031 | Lead React Developer | HIGH | Missing Error Handling | useProjects | src/hooks/useProjects.js:90 | getProject is an async function that calls getDoc without a try/catch. If the Firestore call fails (network error, permission denied), the unhandled promise rejection will crash the caller without any user feedback. | 1. Call getProject with a projectId while offline or with insufficient permissions. 2. The function throws an unhandled error. | The function should catch errors and return null or throw a user-friendly error with a toast notification. | An unhandled promise rejection propagates to the caller with no toast notification or error handling. | Any component calling getProject without its own try/catch will experience unhandled errors, potentially crashing the UI. | OPEN
R01-032 | Lead React Developer | HIGH | Race Condition | useReadabilityAnalysis | src/hooks/useReadabilityAnalysis.js:454 | In analyzeUrl, the abort signal is read from abortControllerRef.current at line 454 before runAnalysis creates a new AbortController at line 309. If analyzeUrl is called twice rapidly, the second call's fetchUrlViaProxy may use the stale signal from the first call's controller, leading to incorrect cancellation. | 1. Call analyzeUrl with URL A. 2. Immediately call analyzeUrl with URL B before the proxy fetch for A completes. 3. Cancel the analysis. 4. The wrong fetch may be cancelled. | Each analyzeUrl invocation should create and use its own isolated abort controller before any async work begins. | abortControllerRef.current is read at line 454 before runAnalysis assigns a new controller at line 309-310, creating a race window. | Users who rapidly re-analyze different URLs may experience incorrect cancellation or zombie network requests. | OPEN
R01-033 | Lead React Developer | MEDIUM | Memory Leak | useFileAttachments | src/hooks/useFileAttachments.js:114 | uploadFile creates a Promise wrapping uploadBytesResumable with state_changed listener callbacks that call setUploading and setUploadProgress. If the component unmounts during upload, these callbacks fire on unmounted state, causing a React memory leak warning. There is no cleanup or mounted check. | 1. Start a file upload via uploadFile. 2. Navigate away from the page before the upload completes. 3. Observe React 'Can't perform a React state update on an unmounted component' warning. | The hook should track mount status with a ref and skip setState calls after unmount, or cancel the upload task on unmount via a useEffect cleanup. | The upload continues in the background and calls setState on an unmounted component when it completes or errors. | Users who navigate away during uploads will trigger console warnings and potentially unstable application state. | OPEN
R01-034 | Lead React Developer | MEDIUM | Race Condition | useReadabilityHistory | src/hooks/useReadabilityHistory.js:114 | loadHistory references `lastDoc` from closure state (line 114) but when called with resetPagination=false, it uses a potentially stale lastDoc value if multiple loadMore calls are triggered before the first completes. This can result in duplicate entries in the history array. | 1. Open the readability history page. 2. Scroll to trigger loadMore rapidly. 3. Observe duplicate analysis entries in the list. | Each pagination request should use the lastDoc from the most recently completed request. | Multiple concurrent loadMore calls all use the same stale lastDoc, fetching the same page multiple times and appending duplicates at line 153. | Users scrolling quickly through history may see duplicate entries and experience inconsistent pagination. | OPEN
R01-035 | Lead React Developer | MEDIUM | State Bug | useReadabilitySettings | src/hooks/useReadabilitySettings.js:61 | updateSettings captures `settings` in its closure (line 61: `const newSettings = { ...settings, ...updates }`). If updateSettings is called twice in rapid succession, the second call will use the stale settings state that doesn't include the first update's changes, overwriting them. | 1. Call updateSettings({ enabledLLMs: ['claude'] }). 2. Immediately call updateSettings({ defaultExportFormat: 'json' }) before the first call completes. 3. Observe that enabledLLMs reverts to the default value. | Each updateSettings call should use the functional updater pattern (setSettings(prev => ...)) to ensure it sees the latest state. | The second call spreads the stale `settings` object, losing the first call's changes. | Users who change multiple settings rapidly will lose some changes, leading to inconsistent preferences. | OPEN
R01-036 | Lead React Developer | HIGH | Race Condition | aiAnalyzer | src/lib/readability/aiAnalyzer.js:52 | analyzeWithAI creates its own AbortController (line 52) and a timeout (line 53), but when the caller passes options.signal, the local controller's abort is never wired to the external signal. The external signal is used as fallback (line 54: `const signal = options.signal ¦¦ controller.signal`), but the local timeout still triggers controller.abort() which has no effect when options.signal is used. Conversely, if the caller aborts via options.signal, the timeout is never cleared. | 1. Call analyzeWithAI with an external signal from useReadabilityAnalysis. 2. The user cancels the analysis via the external signal. 3. The internal 120s timeout still fires after the abort, calling controller.abort() on a controller whose signal is unused. | The timeout should be linked to the actual signal being used. If an external signal is provided, the internal controller and timeout should be coordinated with it. | When options.signal is provided, the internal controller's timeout fires uselessly, and the clearTimeout in finally only clears the internal timeout, not any external abort handling. | Cancelled analyses leave dangling timeouts. Timeout-based aborts fail to actually cancel the request when an external signal is provided. | OPEN
R01-037 | Lead React Developer | LOW | Performance Bug | useFormWithUnsavedChanges | src/hooks/useUnsavedChanges.js:58 | The dirty detection useEffect at line 57-60 uses JSON.stringify to deep-compare `values` and `originalValues` on every render when either changes. For large forms, this is an O(n) operation on every keystroke that could cause UI jank. | 1. Use useFormWithUnsavedChanges with a form containing many fields or large text areas. 2. Type rapidly in a text field. 3. Observe potential lag as JSON.stringify runs on every character. | Dirty detection should use a shallow comparison or a debounced deep comparison to avoid unnecessary serialization on every keystroke. | JSON.stringify is called on both values and originalValues on every state change, creating unnecessary CPU overhead. | Forms with large data sets may experience sluggish typing performance. | OPEN
R01-038 | Lead React Developer | HIGH | Performance Bug | unifiedExportService | src/lib/unifiedExportService.js:6 | unifiedExportService statically imports jsPDF, jspdf-autotable, ExcelJS, and JSZip at module level (lines 6-9). These are large libraries that will be included in the main bundle even if the user never exports anything. The readability export hook (useReadabilityExport.js) correctly uses dynamic imports for these, but unifiedExportService defeats that optimization. | 1. Build the application. 2. Inspect the bundle output. 3. Observe jsPDF, ExcelJS, and JSZip are in the main chunk. | These heavy libraries should be dynamically imported only when an export operation is triggered, as done in useReadabilityExport.js. | Static imports force all three libraries into the main bundle, increasing initial load time by potentially hundreds of KB. | All users pay the cost of loading export libraries on first page load, even if they never use export functionality. | OPEN
R01-039 | Lead React Developer | LOW | Memory Leak | pdfGenerator | src/lib/pdfGenerator.js:301 | previewPDF creates a blob URL with URL.createObjectURL, opens it in a new window, then immediately schedules URL.revokeObjectURL after only 100ms (line 304). If the browser hasn't finished loading the PDF in the new tab within 100ms, the URL is revoked and the preview fails. This is a race condition that manifests as a memory leak (if revoke is delayed) or broken preview (if revoke is too early). | 1. Generate a multi-page PDF. 2. Call previewPDF. 3. On a slow connection or with a large PDF, the 100ms timeout may revoke the URL before the new tab finishes loading. | The blob URL should be revoked when the new window closes, not after an arbitrary 100ms timeout. | The 100ms timeout is a race: either too early (breaking the preview) or the URL is never properly revoked if the window stays open. | Users may see a blank PDF preview tab, or blob URLs accumulate in memory for long-lived browser sessions. | OPEN
R01-040 | Lead React Developer | MEDIUM | Race Condition | auditStorageService | src/lib/audit/auditStorageService.js:297 | getSharedAudit increments viewCount using a read-then-write pattern (reads viewCount at line 269, writes viewCount+1 at line 298). If two users access the shared link simultaneously, both read the same viewCount value and write the same incremented value, losing one view count. | 1. Share an audit link. 2. Two users open the link simultaneously. 3. Both read viewCount=5, both write viewCount=6 instead of 7. | viewCount should be incremented atomically using Firestore's increment() function to handle concurrent access. | Non-atomic read-then-write pattern causes lost updates under concurrent access. | Shared audit view counts will be inaccurate under concurrent access, showing fewer views than actual. | OPEN
R01-041 | Lead React Developer | MEDIUM | Missing Error Handling | useSchemaLibrary | src/hooks/useSchemaLibrary.js:122 | incrementUsage calls updateDoc without a try/catch and references the stale `schemas` array from closure state. If the schema was deleted between renders, the find at line 123 may succeed with stale data but updateDoc will fail with a Firestore 'not found' error that goes unhandled. | 1. Open the schema library. 2. In another tab, delete a schema. 3. In the first tab, use the deleted schema (triggering incrementUsage). 4. An unhandled promise rejection occurs. | incrementUsage should wrap the updateDoc call in a try/catch and handle the case where the schema no longer exists. | The unhandled promise rejection propagates silently, and the stale schemas closure may reference a deleted document. | Concurrent usage across tabs can lead to unhandled errors. The stale schemas closure at line 123 also means the usageCount increment may be based on outdated data. | OPEN
R01-042 | Lead React Developer | LOW | React Anti-Pattern | useReadabilityHistory | src/hooks/useReadabilityHistory.js:318 | Two useEffect hooks at lines 314 and 321 both suppress the react-hooks/exhaustive-deps ESLint rule with eslint-disable-line comments. The effect at line 314 depends on loadHistory but only lists currentUser, and the effect at line 321 omits loadHistory and currentUser. This means filter/sort changes may use stale buildQuery references. | 1. Log in as a user. 2. Change the sort field. 3. In some cases, loadHistory may use a stale buildQuery that doesn't reflect the new sort, returning incorrectly ordered data. | The dependency arrays should properly include all dependencies, or the logic should be restructured to avoid the need for suppressions. | ESLint rules are suppressed, hiding potential stale closure bugs when filters or sort change. | Edge cases where filter/sort changes don't trigger proper reloads, leading to stale data display. | OPEN
R01-043 | Lead React Developer | MEDIUM | Race Condition | useUserProfile | src/hooks/useUserProfile.js:33 | useUserProfile defines an async fetchProfile function inside useEffect and calls it without cancellation logic. If targetUserId changes rapidly (e.g., navigating between user profiles), multiple concurrent fetches race and the last to resolve sets state, which may not correspond to the current targetUserId. | 1. Navigate to user profile A. 2. Immediately navigate to user profile B. 3. If profile A's fetch resolves after profile B's fetch, profile A's data overwrites profile B's display. | A cleanup function should cancel or ignore stale fetch results when targetUserId changes. | All fetches run to completion and the last to resolve wins, regardless of whether its targetUserId is still current. | Users navigating quickly between profiles may briefly see the wrong user's profile data. | OPEN