## Role 1 - Lead React Developer
Bug ID | Role | Severity | Category | Component | File:Line | Description | Steps to Reproduce | Expected Behavior | Actual Behavior | Impact | Status
R01-001 | Lead React Developer | High | Performance | AuthContext | src/contexts/AuthContext.jsx:78 | Context value object is recreated on every render, causing all consumers to re-render unnecessarily | 1. Open React DevTools Profiler 2. Trigger any state change in AuthContext 3. Observe all consuming components re-render | Context value should be memoized with useMemo | Plain object literal in return causes new reference each render | App-wide unnecessary re-renders on every auth state change | OPEN
R01-002 | Lead React Developer | High | Race Condition | AuthContext | src/contexts/AuthContext.jsx:52 | refreshUser async function has no abort mechanism — if component unmounts mid-flight, setState is called on unmounted component | 1. Login 2. Quickly navigate away before profile loads | Async operation should be cancelled on unmount | setState called after unmount, potential memory leak warning | Memory leak and React warning in console | OPEN
R01-003 | Lead React Developer | Medium | Data Integrity | AuthContext | src/contexts/AuthContext.jsx:120 | deleteAccount uses writeBatch but Firestore batches are limited to 500 operations — no pagination for users with many documents | 1. Create user with 500+ documents 2. Attempt account deletion | Batch should be chunked into groups of 500 | Batch exceeds 500 limit and throws | Account deletion fails silently for power users | OPEN
R01-004 | Lead React Developer | Medium | Data Integrity | AuthContext | src/contexts/AuthContext.jsx:115 | listAll() on storage reference returns max 1000 items by default — no pagination for users with many files | 1. Upload 1000+ files 2. Delete account | Storage listing should paginate with pageToken | Only first 1000 files are deleted | Orphaned storage files remain after account deletion | OPEN
R01-005 | Lead React Developer | Medium | Authentication | AuthContext | src/contexts/AuthContext.jsx:95 | Google OAuth re-authentication uses signInWithPopup instead of reauthenticateWithPopup — does not actually re-authenticate the current session | 1. Link Google account 2. Attempt sensitive operation requiring re-auth | Should use reauthenticateWithPopup for proper session re-auth | Creates new sign-in flow instead of re-authenticating | Security-sensitive operations may proceed without proper re-auth | OPEN
R01-006 | Lead React Developer | Medium | Error Handling | AuthContext | src/contexts/AuthContext.jsx:130 | Multiple catch blocks swallow errors with only console.error — no user-facing error feedback | 1. Trigger a Firestore write failure 2. Observe console | Errors should be surfaced to user via toast or state | Errors logged to console only, user sees no feedback | Users unaware of failed operations | OPEN
R01-007 | Lead React Developer | High | Performance | ThemeContext | src/contexts/ThemeContext.jsx:18 | Context value object recreated every render — same pattern as AuthContext | 1. Toggle theme 2. Profile renders | Value memoized with useMemo | New object reference on every render | All theme consumers re-render unnecessarily | OPEN
R01-008 | Lead React Developer | Low | Logic | App | src/App.jsx:45 | useCommandPalette hook runs for unauthenticated users who cannot use any commands | 1. Visit app logged out 2. Press Cmd+K | Command palette should only initialize for authenticated users | Hook runs and registers keyboard listeners for logged-out users | Unnecessary event listeners and potential errors | OPEN
R01-009 | Lead React Developer | Medium | Reliability | lazyWithRetry | src/utils/lazyWithRetry.js:12 | Retry logic uses fixed delay with no exponential backoff — all retries fire at same interval | 1. Simulate network failure on chunk load 2. Observe retry timing | Exponential backoff (1s, 2s, 4s) | Fixed interval retries | Hammers server during outage instead of backing off | OPEN
R01-010 | Lead React Developer | High | Performance | SEOChecklist | src/components/checklist/SEOChecklist.jsx:88 | Debounce timer created inside useCallback — new timer on every callback recreation defeats debounce purpose | 1. Type rapidly in search field 2. Observe network calls | Single debounce timer persists across renders | Timer resets on each render, debounce ineffective | Excessive API calls during search | OPEN
R01-011 | Lead React Developer | High | Stability | SEOChecklist | src/components/checklist/SEOChecklist.jsx:42 | getProject from useProjects likely recreated each render — used in useEffect deps causing infinite fetch loop | 1. Open checklist page 2. Monitor network tab | getProject should be stable (useCallback) or excluded from deps | Infinite re-fetch loop | Infinite API calls, degraded performance, potential rate limiting | OPEN
R01-012 | Lead React Developer | Medium | Performance | AuditPage | src/components/audit/AuditPage.jsx:65 | Large urlData array stored in component state without pagination or virtualization | 1. Upload CSV with 10000+ URLs 2. Observe memory usage | Data should be paginated or virtualized | Entire dataset held in state, rendered in DOM | Browser freezes on large audits | OPEN
R01-013 | Lead React Developer | Medium | Code Quality | ReadabilityPage | src/components/readability/ReadabilityPage.jsx:15 | eslint-disable-next-line suppresses react-hooks/exhaustive-deps — hides genuine missing dependencies | 1. Read source code 2. Note suppressed linting | Fix actual dependency issues instead of suppressing | Lint rule disabled, deps may be stale | Stale closures and unpredictable behavior | OPEN
R01-014 | Lead React Developer | Medium | Performance | ReadabilityPage | src/components/readability/ReadabilityPage.jsx:55 | analysis object passed as prop is not memoized — new reference on every parent render causes child re-renders | 1. Profile component renders 2. Observe unnecessary child re-renders | Object should be memoized with useMemo | New object reference each render | Unnecessary re-renders of all child components | OPEN
R01-015 | Lead React Developer | Medium | Code Quality | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:22 | eslint-disable hides missing useCallback dependencies in effect hooks | 1. Read source 2. Note suppressed warnings | Fix deps properly | Lint suppressed | Stale closures possible | OPEN
R01-016 | Lead React Developer | Low | Code Quality | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:180 | console.log statements left in production code | 1. Open browser console 2. Use readability tool | No console.log in production | Debug logs visible to end users | Information leakage, unprofessional appearance | OPEN
R01-017 | Lead React Developer | Medium | Anti-Pattern | ReadabilityDashboard | src/components/readability/ReadabilityDashboard.jsx:145 | Direct DOM manipulation via document.getElementById instead of using React refs | 1. Read source code at line 145 | Use useRef for DOM access | document.getElementById bypasses React's virtual DOM | Can cause stale references and breaks React's rendering model | OPEN
R01-018 | Lead React Developer | Medium | Anti-Pattern | ReadabilityInputScreen | src/components/readability/ReadabilityInputScreen.jsx:35 | Direct localStorage.getItem call in render body — side effect during render phase | 1. Read source code | Read localStorage in useEffect or useMemo | Synchronous side effect in render | Violates React rules, can cause issues with SSR/concurrent mode | OPEN
R01-019 | Lead React Developer | Low | Anti-Pattern | ReadabilityInputScreen | src/components/readability/ReadabilityInputScreen.jsx:92 | Hacky re-render trigger via setForceRerenderKey(Date.now()) instead of proper state management | 1. Read source code at line 92 | Use proper state updates to trigger re-renders | Artificial key change forces unmount/remount | Loses component state, poor performance pattern | OPEN
R01-020 | Lead React Developer | Medium | State Management | ReadabilityInputScreen | src/components/readability/ReadabilityInputScreen.jsx:110 | Paste handler updates fileContent state but desyncs from displayed textarea value | 1. Paste content into textarea 2. Edit pasted content 3. Submit | Pasted content and display should stay in sync | State diverges from displayed value after edit | User submits different content than what they see | OPEN
R01-021 | Lead React Developer | Medium | Consistency | ReadabilityLLMPreview | src/components/readability/ReadabilityLLMPreview.jsx:22 | LLM model names (Claude 3.5 Sonnet, Gemini 1.5 Pro) inconsistent with ProcessingScreen (Claude Sonnet 4.5, Gemini 2.0 Flash) | 1. Compare LLM_OPTIONS in LLMPreview vs LLM_SUBSTAGES in ProcessingScreen | Same model names across components | Different model names/versions referenced | Confusing UX, users see different model names in different views | OPEN
R01-022 | Lead React Developer | Low | Performance | ReadabilityLLMDiff | src/components/readability/ReadabilityLLMDiff.jsx:45 | Uses array index as React key in diff output mapping | 1. Read source code | Stable unique keys | Index-based keys | Inefficient reconciliation when diff changes | OPEN
R01-023 | Lead React Developer | Low | Consistency | ReadabilityHistory | src/components/readability/ReadabilityHistory.jsx:88 | Uses gray-* Tailwind classes while rest of app uses charcoal-* custom palette | 1. Compare class names with other components | Consistent charcoal-* palette usage | Mixed gray-* and charcoal-* classes | Visual inconsistency in dark mode | OPEN
R01-024 | Lead React Developer | High | Memory Leak | ReadabilityScoreCard | src/components/readability/ReadabilityScoreCard.jsx:59 | useAnimatedScore hook uses requestAnimationFrame without cleanup — if component unmounts mid-animation, setCurrent called on unmounted component | 1. Navigate to score card 2. Quickly navigate away during animation | Cancel rAF on unmount via cleanup function | rAF continues firing after unmount | Memory leak and React state-update-on-unmounted warning | OPEN
R01-025 | Lead React Developer | Medium | Security | ReadabilityBadgeGenerator | src/components/readability/ReadabilityBadgeGenerator.jsx:85 | dangerouslySetInnerHTML renders SVG with interpolated score prop — if score contains unexpected string values, potential XSS | 1. Pass non-numeric score prop 2. Inspect rendered HTML | Sanitize or use React SVG elements instead | Raw HTML injection via dangerouslySetInnerHTML | Potential XSS if score prop is tampered | OPEN
R01-026 | Lead React Developer | Low | Error Handling | ReadabilityShareView | src/components/readability/ReadabilityShareView.jsx:98 | PDF export error caught but only logged to console — no user-facing error notification | 1. Trigger PDF export failure 2. Check for user feedback | Show toast or error message to user | console.error only | User doesn't know export failed | OPEN
R01-027 | Lead React Developer | Medium | Race Condition | ReadabilityShareView | src/components/readability/ReadabilityShareView.jsx:87 | loadSharedAnalysis async call has no abort/cleanup on unmount | 1. Open shared link 2. Navigate away quickly | Abort controller or mounted flag | Async completes and updates unmounted state | Memory leak warning | OPEN
R01-028 | Lead React Developer | Medium | Logic | ReadabilityBenchmarkWidget | src/components/readability/ReadabilityBenchmarkWidget.jsx:75 | calculatePercentile computes rank against user's OWN scores, not population — always shows ~50th percentile for consistent users | 1. Run 10 analyses with similar scores 2. Check percentile | Percentile against population or clear labeling | Self-referential percentile is meaningless | Misleading metric displayed to users | OPEN
R01-029 | Lead React Developer | High | State Management | ReadabilityWeightConfig | src/components/readability/ReadabilityWeightConfig.jsx:26 | useState initialized from props — if parent passes new weights prop, local state never updates (stale props pattern) | 1. Parent updates weights prop 2. Observe component still shows old values | Sync state with props via useEffect or controlled pattern | Initial prop value frozen in state | UI shows stale weight values after external changes | OPEN
R01-030 | Lead React Developer | Medium | Race Condition | ReadabilityProjectTagger | src/components/readability/ReadabilityProjectTagger.jsx:110 | onBlur={handleAddTag} races with onClick on suggestion buttons — blur fires first, adding partial input before click registers | 1. Type partial tag 2. Click a suggestion from dropdown | Suggestion click should work cleanly | Partial text added as tag, then suggestion also added | Duplicate/garbage tags created | OPEN
R01-031 | Lead React Developer | Medium | Dead Links | ReadabilityCrossToolLinks | src/components/readability/ReadabilityCrossToolLinks.jsx:50 | Links to /app/content-planner and /app/keyword-research routes that don't exist in App.jsx route definitions | 1. Run readability analysis on URL 2. Click 'Plan Content Updates' or 'Research Keywords' | Links navigate to working routes | 404 or blank page | Broken navigation, user frustration | OPEN
R01-032 | Lead React Developer | High | Routing | ProjectDashboard | src/components/projects/ProjectDashboard.jsx:186 | Empty state CTA navigates to /planner/new but header button uses /app/planner/new — inconsistent route prefixes | 1. View project dashboard with zero projects 2. Click 'Create Your First Project' | Both buttons navigate to same route | /planner/new likely 404s (missing /app prefix) | Broken navigation for new users | OPEN
R01-033 | Lead React Developer | Medium | Error Handling | ProjectCreationWizard | src/components/projects/ProjectCreationWizard.jsx:161 | handleSubmit catch block only logs to console — no user-facing error message on project creation failure | 1. Trigger Firestore write failure during project creation | Toast or inline error shown to user | console.error only, loading spinner stops | User thinks creation succeeded when it failed | OPEN
R01-034 | Lead React Developer | High | Routing | ProjectCreationWizard | src/components/projects/ProjectCreationWizard.jsx:159 | After project creation, navigates to /planner/projects/${projectId} — missing /app prefix | 1. Create a project successfully | Navigate to /app/planner/projects/${id} | Navigates to /planner/projects/${id} — likely 404 | User sees 404 after successful project creation | OPEN
R01-035 | Lead React Developer | Low | Performance | MyTasksPage | src/components/projects/MyTasksPage.jsx:314 | Uses array index as key for task list items instead of unique task identifier | 1. View My Tasks page with multiple tasks | key={task.id} or similar unique identifier | key={index} | Incorrect DOM reconciliation when tasks reorder | OPEN
R01-036 | Lead React Developer | High | Routing | MyTasksPage | src/components/projects/MyTasksPage.jsx:97 | handleTaskClick navigates to /projects/${task.projectId} — missing /app prefix | 1. Click any task in My Tasks list | Navigate to /app/projects/... | Navigates to /projects/... — 404 | All task detail navigation is broken | OPEN
R01-037 | Lead React Developer | Critical | Data Integrity | ProgressDashboard | src/components/projects/ProgressDashboard.jsx:352 | Math.random() used for project stats (completed count, percentage, critical items) — production dashboard shows random data on every render | 1. Open Progress Dashboard 2. Refresh page 3. Observe different numbers each time | Stats computed from actual Firestore data | Random numbers displayed as real project metrics | Dashboard is completely unreliable — shows fabricated data to users | OPEN
R01-038 | Lead React Developer | High | Stability | ProjectHealthReport | src/components/projects/ProjectHealthReport.jsx:150 | getProject in useEffect dependency array — likely recreated each render by useProjects, causing infinite fetch loop | 1. Open any project health report 2. Monitor network tab | Stable function reference via useCallback | Infinite re-fetch loop | Infinite API calls, degraded performance | OPEN
R01-039 | Lead React Developer | Medium | Accessibility | ProjectHealthReport | src/components/projects/ProjectHealthReport.jsx:48 | ProgressRing SVG uses hardcoded hex colors (#E5E7EB, #0066FF) that don't respect dark mode | 1. Switch to dark mode 2. View health report | Colors adapt to dark mode | Light-mode colors on dark background | Poor contrast and visibility in dark mode | OPEN
R01-040 | Lead React Developer | High | Build | ProjectLinkedItems | src/components/projects/ProjectLinkedItems.jsx:208 | Dynamic Tailwind classes bg-${color}-100 text-${color}-700 are purged at build time — classes won't exist in production CSS | 1. Build production bundle 2. View linked items type summary | Use static class mappings | Dynamic interpolation purged by Tailwind JIT | Type badges have no styling in production | OPEN
R01-041 | Lead React Developer | High | Functional | ProjectCard | src/components/projects/ProjectCard.jsx:24 | completionPercentage hardcoded to 0 with '// Placeholder' comment — every project card shows 0% progress | 1. Open Project Dashboard 2. Observe all cards show 0% | Actual completion calculated from checklist data | Hardcoded const completionPercentage = 0 | Progress tracking is non-functional across all project cards | OPEN
R01-042 | Lead React Developer | High | Routing | ProjectCard | src/components/projects/ProjectCard.jsx:82 | View Checklist navigates to /planner/projects/${id} — missing /app prefix | 1. Click View Checklist on any project card | /app/planner/projects/${id} | /planner/projects/${id} — 404 | Primary project navigation broken | OPEN
R01-043 | Lead React Developer | Medium | Accessibility | AuditHistoryPanel | src/components/audit/AuditHistoryPanel.jsx:113 | ComparisonModal lacks focus trap, keyboard escape handling, and aria-modal attribute | 1. Open comparison modal 2. Press Tab repeatedly 3. Press Escape | Focus trapped in modal, Escape closes it | Focus escapes to background, Escape does nothing | Keyboard/screen reader users cannot use comparison feature properly | OPEN
R01-044 | Lead React Developer | High | Build | AuditHistoryPanel | src/components/audit/AuditHistoryPanel.jsx:166 | Dynamic Tailwind class text-${cat.color}-500 will be purged at build — same issue as ProjectLinkedItems | 1. Build production 2. Open comparison modal | Static class mapping | Dynamic interpolation purged | Category icons lose color in production build | OPEN
R01-045 | Lead React Developer | Medium | Performance | useProjects | src/hooks/useProjects.js:28 | onSnapshot listener has no error callback — Firestore listener errors are silently dropped | 1. Lose network connection 2. Observe no error UI | Error callback handles and surfaces Firestore errors | Error silently swallowed | Users unaware of data sync failures | OPEN
R01-046 | Lead React Developer | High | Race Condition | useChecklist | src/hooks/useChecklist.js:45 | toggleItem optimistic update can be reverted by stale onSnapshot callback — race between local toggle and server response | 1. Rapidly toggle same item 2. Observe flickering state | Optimistic update reconciled with server state | onSnapshot overwrites optimistic toggle | Checklist items flicker and may show wrong state | OPEN
R01-047 | Lead React Developer | Medium | Performance | useAudits | src/hooks/useAudits.js:35 | Stats object computed but not memoized — recalculated on every access | 1. Profile component renders | Stats wrapped in useMemo | Computed inline | Unnecessary recalculations | OPEN
R01-048 | Lead React Developer | Medium | Data Integrity | useNotifications | src/hooks/useNotifications.js:62 | writeBatch for mark-all-read has no 500-operation limit check | 1. Accumulate 500+ unread notifications 2. Click Mark All Read | Batch chunked to 500-op limit | Batch exceeds limit and throws | Mark-all-read fails for users with many notifications | OPEN
R01-049 | Lead React Developer | Medium | Performance | useAssignments | src/hooks/useAssignments.js:80 | useMyTasks fetches ALL assignment documents then filters client-side — no server-side query filtering | 1. Open My Tasks with 1000+ assignments in system | Firestore query with where clause for current user | Fetches all, filters in JS | Excessive bandwidth and slow load for large teams | OPEN
R01-050 | Lead React Developer | Medium | Logic | useDueDates | src/hooks/useDueDates.js:30 | Computed overdue/upcoming values cached but stale after midnight — no timer to refresh date-dependent computations | 1. Leave app open overnight 2. Check due date indicators next morning | Date computations refresh at midnight or periodically | Values computed once and cached until next state change | Tasks shown as 'due today' when actually overdue | OPEN